General Services Administration

IT Budget Submission Instructions

Guide for Major IT Initiatives

(BY2009 Exhibit 300 & Exhibit 53)

Office of the Chief Information Officer

July 2007

Document Change Record

| Version Number | Date | Description | OMB A-11 | Major Changes to the Version |
| --- | --- | --- | --- | --- |
| 1.0 | June 14, 2006 | Version 1.0 Draft Document | Based on the BY08 95% solution |  |
| 1.1 | June 17, 2006 | Version 1.1 Updated for all Major Initiatives | Based on the BY08 95% solution | Updates to Schedule (p.5) |
| 2.0 | July 12, 2006 | Version 2.0 Updated from feedback of Major Initiatives | Based on the BY08 99% solution | Updates to Schedule (p.5); Changes to the Funding Sources Table and MAX Account additions (p.12 & 69); Provided Points of Contact (p.68); Provided eCPIC administrative details, including XML validation (p.7-8); Identified High Risk projects (p.17); Clarified year of budget submission field (p.14); Provided PM qualification guidance (p.17); Added clarification on the Contracts table (p.28); Specified Table 2 as the appropriate Performance table (p.30); Identified source for PIA availability (p.25) |
| 2.1 | July 31, 2006 | Version 2.1 Updated from eCPIC Training | Based on the BY08 100% solution | Further Guidance on the Performance Baseline tables (p. 44, 46, & 54); EVM appendix (p.70-80); Updates to the Points of Contact (p.68); Crosswalk to eCPIC screens to include cross-over 53 data in the 300 process guidance (p.9-14); Versioning Guidance (p.2); Updates to Contracts Table (p.28); Updates to schedule (p.5); Updates to MAX accounts (p.12 & 69) |
| 3.0 | June 1, 2007 | Version 3.0 Draft Document | Based on the BY09 95% solution | Added additional content. Incorporated Evaluation Framework and updated Alternatives Analysis guidance. |
| 3.1 | June 27, 2007 | Version 3.1 Draft Document | Based on the BY09 98% and Exhibit 300 Evaluation Framework Version 3.0 | Added eCPIC screenshots. |

Section 1: Introduction	4

Section 2: Overview of Exhibit 300 Template	5

Section 3: Schedule of Budget Submission Activities	6

Section 4: eCPIC & XML Validation	9

Section 5: Guidance for Completing the Exhibit 300	11

Part I: Summary Information and Justification	12

Part I.A: Overview	12

Part I.B:  Summary of Spending BY09	26

Part I.C Acquisition/Contract Strategy BY09	33

Part I.D Performance Information BY09	37

Part I.E Security and Privacy BY09	39

Part I.F:  Enterprise Architecture BY09	46

Part II: Planning, Acquisition and Performance	52

Part II.A:  Alternatives Analysis	52

Part II.B: Risk Management BY09	56

Part II.C: Cost and Schedule Performance BY09	58

PART III : For “Operation and Maintenance” initiatives ONLY (Steady State)	61

III.A: Risk Management Plan BY09	61

III.B: Cost Schedule and Performance BY09	63

PART IV: Planning For “Multi-Agency Collaboration” ONLY	65

Part IV.A:  Multi-Agency Collaboration Oversight (All Capital Assets)	65

Part IV: Alternatives Analysis (DME/Mixed Lifecycle only)	68

Part IV Risk Management (DME/Mixed Lifecycle):	68

Part IV Risk Management (O&M initiatives only)	68

Part IV Cost and Schedule Performance Information (DME/Mixed Lifecycle)	68

Part IV: Cost and Schedule Performance Information (O&M Lifecycle)	68

APPENDIX A:	69

QUANTITATIVE APPROACH FOR CONDUCTING ALTERNATIVES ANALYSIS	69

APPENDIX B:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY SUBJECT AREA	79

APPENDIX C:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY INITIATIVE	80

APPENDIX D:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY BUDGET AREA	81

APPENDIX E:   GSA FUNDING SOURCE	82

APPENDIX F:   BY09 GUIDE TO IT PORTFOLIO MANAGEMENT ITEMS	83

APPENDIX G:   BY09 EXHIBIT 300 EVALUATION FRAMEWORK	89

# Section 1: Introduction

The General Services Administration (GSA) is required to submit Exhibit 300s, or Capital Asset Plans, for all of its major Information Technology (IT) initiatives. GSA submits the Exhibit 300s to the Office of Management and Budget (OMB) as part of the Agency’s budget request. OMB reviews the Exhibit 300s and uses these business cases as part of its decision making for agency budget requests. The Exhibit 300 also helps OMB meet its statutory requirements under a host of laws, such as the Government Performance Results Act (GPRA) and the Clinger-Cohen Act.

Exhibit 300s are an important part of GSA’s Capital Planning and Initiative Control (CPIC) process mandated by the Clinger-Cohen Act.  The Exhibit 300 is required by OMB for all major capital assets of government agencies.  Due to the significant amount of federal resources tied to IT and concerns and questions about the rigor of management review, analysis, and control over those initiatives, the Exhibit 300 requires additional information on major IT initiatives.

At GSA, a major IT initiative is a system, program, and/or project (s) that meets the following criteria:

- Requires special management attention because of the initiative’s importance to agency mission;

- Served as a major initiative in the previous year and is continuing;

- Is for a financial system and spends more than $500,000 annually;

- Is directly tied to the top two layers of the Federal Enterprise Architecture (Services to Citizens and Mode of Delivery);

- Is an integral part of the agency’s modernization blueprint (Enterprise Architecture Target vision);

- Has significant program or policy implications;

- Has high-level executive visibility; or

- Is defined as a major by the CPIC process.

GSA uses the Exhibit 300 to document for OMB how the Agency’s capital planning and initiative control process works. Additionally, the Exhibit 300 provides the means by which GSA can describe how its IT initiatives align with the Agency’s strategic goals and business decisions. It provides data that will allow the Agency to make better funding decisions and to identify initiatives that are performing well or performing poorly.  The use of a common format provides both GSA and OMB the opportunity to compare initiative data and make targeted decisions for competing funding priorities.

Additionally, as a federal agency, GSA is required to submit its Agency IT Investment Portfolio in a common reporting format, referred to as the Exhibit 53.  The Exhibit 53 encompasses both major and non-major initiatives to be reported for the BY08 budget process.  All required Exhibit 53 data fields are included within the Exhibit 300 workflow in eCPIC, the Agency’s budget submission tool, and are included as part of this guide.

# Section 2: Overview of Exhibit 300 Template

The Exhibit 300 template is structured as a series of questions and tables designed to capture specific data from the initiative owner.  The BY2009 submission template has minor changes compared to the BY2008 format.  Initiatives will continue to submit only the data in the sections that are applicable to their phase/type.  For example, a mixed life cycle initiative will have different reporting requirements than a steady state initiative. Refer to Section V of this document for guidance in completing each section of the Exhibit 300.  An overview of the BY09 submission template is listed below:

Part I: Summary Information and Justification

Complete Sections A, B, C, and D for all capital assets (including IT and non-IT)

Complete Sections E and F for IT capital assets only. Part I includes the following:

- Section A:  Overview

- Section B:  Summary of Funding

- Section C:  Acquisition/Contract Strategy

- Section D:  Performance Information

- Section E:  Security and Privacy

- Section F:  Enterprise Architecture

Part II: Planning, Acquisition & Performance Information

Complete Section II only for initiatives which will be in Planning, Full Acquisition, or Mixed Life Cycle phases in FY2009.  Part II includes the following:

- Section A:  Alternative Analysis

- Section B:  Risk Management

- Section C:  Cost and Schedule Performance

Part III: For “Operation & Maintenance” initiatives ONLY (Steady State)

Complete Section III only for initiatives which will be in the Operations & Maintenance (Steady State) phase in FY2009.  Part III includes the following:

- Section A:  Risk Management

- Section B:  Cost and Schedule Performance

Part IV: For “Multi-Agency Collaboration” initiatives ONLY

Complete Section IV only for initiatives which will be managing an E-Gov initiative or Line of Business in FY2009.  Part IV includes the following:

- Section A:  Multi-Agency Collaboration Oversight

- Section B:  Risk Management

- Section C:  Cost and Schedule Performance

# Section 3: Schedule of Budget Submission Activities

Exhibit 300s are due to OCIO for internal evaluation no later than July 30th, 2007. Feedback will be distributed on a bi-weekly basis regarding the initiative’s Exhibit 300 evaluation status from July 30th – September 4th.  Final Exhibit 300s are due to OCIO on Tuesday, September 4th, and will be submitted to OMB on Monday, September 10th.  For more information on the Exhibit 300 Evaluation Framework, please see Appendix G.

A schedule of all budget submission activities, as well as responsible parties associated with each activity, is detailed on the next page. These activities include the key dates for the internal evaluation. OCIO is responsible for coordinating the ratings of the team of subject matter experts (SMEs) participating in the reviews. OCIO will distribute status updates to the Staff and Services Offices on a bi-weekly basis.  Additionally, OCIO will support program managers (PMs) and business owners by offering multiple training sessions and other informational sessions.

Figure 1:  Schedule of Budget Submission Activities

All Exhibit 300s will be evaluated by OCIO Capital Planning Staff, in conjunction with subject matter experts (SMEs) from the Office of the Chief Financial Officer (OCFO) budget office, OCIO Enterprise Architecture, OCIO Security, Office of the Chief Acquisition Officer (OCAO) and Office of the Chief Human Capital Officer (OCHCO) Privacy offices. Figure 2 is a map of the roles and responsibilities for the Exhibit 300 Evaluation process.

Figure 2:  Exhibit 300 Review Process Flow

# Section 4: eCPIC & XML Validation

Extensible Markup Language, or XML, is the format that OMB requires for Exhibit 300s submissions.  The eCPIC tool, which is GSA’s central repository for IT business case information, has the capacity to export the Exhibit 300s to OMB in XML. Before submitting your initiative’s Exhibit 300 to OCIO, initiative owners must test the XML export to ensure that no “error” messages are received by clicking the XML 300 icon noted in the eCPIC screenshot below.

Figure 3:  XML Validation Screenshot

If an “error” message is received, follow the appropriate directions under XML errors to correct the error in the relevant section of the 300 before submitting it to OCIO. See Figure 4 below for an eCPIC screenshot of sample errors.

Figure 4:  XML Error Screenshot

While “warning” messages should also be corrected, they do not prohibit transmitting the XML export to OMB. Warning messages typically alert the user to errors in business logic. For example, if the user indicates that the initiative is a Steady State-only initiative within the Screening questions, but then fills out Part II of the Exhibit 300 (for DME/Mixed Lifecycle Initiatives), the user will receive a business logic warning.

Dennis Papula, GSA OCIO, (dennis.papula@gsa.gov) can be contacted for further assistance regarding eCPIC XML validation.

# Section 5: Guidance for Completing the Exhibit 300 & Exhibit 53

This guide should serve as a template with helpful hints and suggestions when completing your initiative’s business case. The guide is structured to follow the current format of the Exhibit 300 in GSA’s eCPIC tool, and is inclusive of all Exhibit 53 questions. The OMB defined template has character limits for certain fields in eCPIC, as follows:

- Short: 255 characters

- Medium: 500 characters

- Long: 2500 characters

There is a counter in eCPIC which will advise the remaining characters that are available on constrained fields. The user should save frequently (approximately once/15 minutes) to avoid timing out within the system.

## Part I: Summary Information and Justification

### Part I.A: Overview

Several of the questions listed below are also required in the Exhibit 53 and will cross-populate within eCPIC.

Initiative Definition:  In order to create a new initiative in eCPIC, users must contact their OCIO liaison.  For ongoing initiatives, OCIO has created a new revision of all initiatives in the BY09 process in eCPIC.

Figure 5:  Initiative Definition BY09

Descriptive Information:  Verify and update the initiative information shown in Figure 6 below:

Figure 6: Descriptive Information BY09

1. Date of Submission: This response should be consistent with the initial reporting deadline included in Circular A-11 for the 09 budget cycle. For BY09, this date is scheduled for September 10, 2007.

2. Agency: Insert “General Services Administration” or applicable agency code.

3. Bureau:  Identify the Bureau name.

4. Name of This Capital Asset:  Identify the name of this initiative.

5. Full UPI Code:  The Unique Project Identifier (UPI) code is generated from Section 53.8.

Note: Fields “Agency” – “Full UPI Code” are required in the Exhibit 53 and will cross-populate into the BY09 Exhibit 300 workflow in eCPIC.

5a. Four Digit UPI Code:  This is a four digit identification number that identifies a specific IT initiative. If a new initiative is added to the Exhibit 53, locate the area of the Exhibit 53 where you are going to report the IT initiative. Then, contact the OCIO Capital Planning Group (Dennis Papula, 202-219-0180) for assignment of  the next sequential number as your four digit identification number.

5b. Two Digit UPI Code:  These two digits identify which part of the initiative you are reporting.  Select one of the following two digit codes according to what you report on the title line:

00 = Total initiative title line, or the first time the agency is reporting this particular initiative.  If this is one of the PMC E-Gov initiatives or an individual agency’s participation in one of the PMC E-Gov initiatives, this two-digit code should be “24”.

04 = Funding source or appropriation

07 = High-Risk Project as part of a larger initiative (Migration projects may not use this code, these are defined by use of IT migration initiative type)

09 = Any subtotal

5c. Exhibit 53 Part:  These two digits indicate the five parts of the Exhibit 53:

01 = Part 1. IT Initiatives by Mission Area

02 = Part 2. IT Initiatives for Infrastructure, Office Automation, and Telecommunications

03 = Part 3. IT Initiatives for Enterprise Architecture and Planning

04 = Part 4. IT Initiatives for Grants Management Systems

05 = Special Use IT Initiatives (Grants to State and Local, National Security Systems)

06 = National Security Systems initiatives

Most major GSA initiatives will be classified as 01. Initiatives associated with the Enterprise Infrastructure Operations (EIO) will be classified as 02. The GSA Enterprise Architecture Program will be classified as 03.

5d. OMB Investment Type:  The two digits indicate your agency's type of initiative. Select one of the following four two-digit codes according to the type of initiative you are reporting:

01 = Major IT initiatives

Classify initiatives as major if it meets any of the following criteria:

- Requires special management attention because of the initiative’s importance to agency mission;

- Served as a major initiative in the previous year and is continuing;

- Is for a financial system and spends more than $500,000 annually;

- Is directly tied to the top two layers of the Federal Enterprise Architecture (Services to Citizens and Mode of Delivery);

- Is an integral part of the agency’s modernization blueprint (Enterprise Architecture Target vision);

- Has significant program or policy implications;

- Has high-level executive visibility; or

- Is defined as a major by the CPIC process

02 = Non-major IT initiatives

Classify your initiative as non-major if it does not qualify as a major initiative according to any of the above criteria.

03 = IT migration initiative portion of a larger asset and for which there is an existing business case for the overall asset.  Description of the IT initiatives should indicate the UPI of the major asset initiative of the managing partner. For example, at some agencies, the eCPIC tool could be coded as “03” if it supports a “Capital Planning and Initiative Control” Exhibit 300 business case.

04 = Partner agency funding contribution represents resources provided by partner agency for a joint effort for more than one agency.  Use the 04 indicator to identify projects where the business case for the major IT initiative is reported in another agency’s exhibit 53.  The description of the IT initiative should indicate the UPI of the major asset initiative of the managing partner.

5e. OMB Exhibit 53 Major Mission Area:  Staff and Service Offices’ Mission Areas and corresponding two digit unique codes are listed below.

01: Financial Management

02: Office of the Chief Acquisition Officer (OCAO)

05: Office of the Chief Human Capital Officer (OCHCO)

06: Office of Governmentwide Policy (OGP)

07: Office of the Inspector General (OIG)

08: Public Building Service (PBS)

09: Office of Citizen Services and Communications

11: eGov Partnering Contributions

12: Office of the Chief Information Officer (OCIO)

14: Federal Acquisition Service (FAS)*

* Note – Federal Supply Service (FSS) and Federal Technology Service (FTS) were formerly 03 and 04, respectively. The new code became effective as of the BY08 Budget Submission.

When reporting initiatives that are being funded by another SSO, ensure that the initiative is located under the appropriate mission area, i.e., the mission area that is funding the initiative.

5f. PY Full UPI Code:  This number should be consistent with the Prior Year Full UPI code that was presented on the Exhibit 53 & Exhibit 300.

Note: Questions 5a – 5f are required in the Exhibit 53 and will cross-populate into the BY09 Exhibit 300 workflow in eCPIC.

6. What kind of investment will this be in FY2009: This section must be filled out accurately for all initiatives. If the data is incorrect, the corresponding incorrect sections of the business case will be sent to OMB. For example, an E-Gov initiative must check the appropriate box for “Multi-Agency Collaboration E-Gov” in order for eCPIC to send Parts I & IV to OMB for that initiative. Initiatives moving to O&M ONLY in FY2009, with Planning/Acquisition activities prior to FY2009, should not select O&M. These initiatives should indicate their current status.

Identify the phase of the initiative from the following options:

- Planning: Includes the initial planning steps and early concept development. Example tasks include Request for Proposal (RFP) development, proposal evaluation, project plan and schedule development, needs assessment, feasibility studies, and risk analysis.

- Full Acquisition: Relates to the procurement and implementation of a project, which occurs after all planning activities are complete and baseline cost and schedule, and performance goals are established.

- Operations & Maintenance:  Includes an initiative that is operational and only needs to perform maintenance to remain stable.

- Mixed Life Cycle: Includes an initiative that has DME and SS aspects.

- E-Gov/LoB Oversight Multi-Agency Collaboration: Includes multi-agency initiatives, including E-Gov and LoB initiatives.

6a. If this initiative supports homeland security, indicate by corresponding number which homeland security mission area(s) this initiative supports:  Determine whether or not the initiative supports the Homeland Security efforts of the country by using the following Homeland Security goals and objectives as a guide:

1) Intelligence and warning

2) Border and transportation security

3) Defending against catastrophic threats

4) Protecting critical infrastructure and key assets

5) Emergency preparedness and response

6) Other

If the initiative supports one of these mission areas, indicate which one(s) by listing the corresponding number(s) listed above. If the initiative does not support homeland security, please leave blank.

6b.  OMB Short Description:  Provide a project description of two hundred and fifty-five words or less.  The description should explain the initiative, its components, and the functionality that it provides.

6c.  Initiative C&A Status:  Initiative owners should provide the current C&A status of the initiative’s system(s):

(00)–Systems within this initiative have not been through the C&A process because the initiative is not yet operational.

(02)-None of the systems have gone through the C&A process or have been granted full authority to operate (for operational initiatives)

(22)-Some or all of the systems within this initiative have been through a C&A process, but no systems have been granted full authority to operate.

(25)-Some or all of the systems within this initiative have been through a C&A process, and some systems have been granted full authority to operate.

(55)-All of the systems within this initiative have been through a C&A process and they have been granted full authority to operate.

Note: The homeland security indicator – C&A Status fields are required in the Exhibit 53 and will cross-populate into the BY09 Exhibit 300 workflow in eCPIC.

Screening Questions BY09: Verify and update the initiative information shown in Figure 7:

Figure 7:  Screening Questions BY09

7. What was the first budget year this initiative was submitted to OMB? Identify the budget year this initiative was initially submitted to OMB (e.g., “FY2001 or earlier” through “FY2009”). eCPIC will have a drop-down box that will indicate no dates earlier than the “FY 2001 or earlier” category.

8. Provide a brief summary and justification for this initiative, including a brief description of how this closes in part or in whole an identified agency performance gap:  Identify the functions supported by the initiative.

9. Did the Agency’s Executive/Initiative Committee approve this request?  “Yes” should be selected.

9a. If “Yes,” what was the date of this approval? Enter July 23, 2007 - the date of the Business Systems Council meeting.

10. Did the Project Manager review this Exhibit?  The GSA Certified Project (or Program) Manager for this initiative should review the Exhibit 300. The “Yes” selection should be chosen.

11. Contact information of Project Manager?  The GSA Certified Project Manager who reviewed the Exhibit 300 should provide the appropriate contact information, including phone number and email address.

11a.  What is the current Federal Acquisition Certification for Program and Project Managers (FAC-P/PM) certification level of the project/program manager? This question refers to a PM’s alignment to the Federal Acquisition Certification level required for PMs. GSA initiative owners should work with the Office of the Chief Acquisition Office to identify the most appropriate selection:

- Entry/Apprentice-level

- Mid/Journeyman-level

- Senior/Expert-level

- Defense Acquisition Workforce Improvement Act (DAWIA)-Level-1

- DAWIA-Level-2

- DAWIA-Level-3

- TBD

12. Has the agency developed and/or promoted cost effective, energy-efficient and environmentally sustainable techniques or practices for this project? Select “Yes” or “No” as appropriate for the initiative.

12a. Will this initiative include electronic assets (including computers)? Select “Yes” or “No” as appropriate for the initiative.

12b.	Is this initiative for new construction or major retrofit of a Federal building or facility? (Answer applicable to non-IT assets only.):   Major GSA IT initiatives should answer no for this question.

1.  If “Yes” is an ESPC or UESC being used to help fund this initiative? Select ”Yes” or “No” as appropriate for the initiative. An Energy Saving Performance Contract (ESPC) achieves an energy reduction goal through an alternative financing arrangement where Federal agencies contract with energy service companies, which pay all the up-front costs. These costs include identifying building energy requirements and acquiring, installing, operating, and maintaining the energy-efficient equipment. In A Utility Energy Services Contract (UEAC), a utility generally arranges financing to cover the capital costs of the project. Then the utility is repaid over the contract term from the cost savings generated by the energy efficiency measures. Therefore, the initial capital initiative is minimal.

2.  If “yes,” will this initiative meet sustainable design principles? Select “Yes” or “No” as appropriate for the initiative. Sustainable design refers to the principle of designing physical objects to comply with the principles of economic, social, and ecological sustainability.

3.  If “yes,” is it designed to be 30% more energy efficient than relevant code? Select “Yes” or “No” as appropriate for the initiative.

13. Does this initiative directly support one of the PMA initiatives? Select “Yes” or “No” as appropriate for the initiative. The President’s Management Agenda contains five government-wide and nine agency-specific goals to improve federal management and deliver results that matter to American people.  The President’s Management Agenda is available at http://www.whitehouse.gov/omb/budget/fy2002/mgmt.pdf.

13a.  If “yes,” check all that apply: Select the appropriate PMA categories that the initiative supports:

- Human Capital

- Budget Performance Integration

- Financial Performance

- Expanded E-Government

- Competitive Sourcing

- Faith Based and Community

- Real Property Asset Management

- Eliminating Improper Payments

- Privatization of Military Housing

- Research & Development Initiative Criteria

- Housing & Urban Development Management & Performance

- Broadening Health Insurance Coverage through State Initiatives

- “Right Sized” Overseas Presence

- Coordination of VA & DoD Programs and Systems

13b. Briefly and specifically describe for each selected how this asset directly supports the identified initiative(s)? (e.g.,  If E-Gov is selected, is it an approved shared service provider or the managing partner?)  Provide a sound justification for how the initiative directly supports the selected categories using a medium text-field description (i.e., 500 characters or less).

OMB typically assesses each Exhibit 300 for alignment with the President’s Management Agenda. To perform well in this area, the Exhibit 300 must (1) have a project summary indicating the gaps filled by this initiative alignment with the PMA, and/or evidence that this is a collaborative initiative that includes industry, multiple agencies, state, and/or local governments; (2) support one or more of the PMA initiatives and include a description of the contribution that is specific and measurable; (3) identify outcomes consistent with the PART outcomes, if applicable; (4) demonstrate that an eGov strategy review is underway (applicable to SS initiatives only); and (5) maintain performance goals are consistent with the contribution to the PMA initiatives selected.

14.  Does this initiative support a program assessed using the OMB’s Program Assessment Rating Tool (PART)?  (For more information about the PART, visit www.whitehouse.gov/omb/part.) If your initiative was included in the 2007 PART review, indicate “Yes” as the appropriate response.  Programs within GSA undergoing a 2007 PART review included:

- Global Supply

- Information Technology Solutions

- National Furniture Center

- New Construction

- Office of Governmentwide Policy

- Personal Property Management

- Real Property Disposal

- Real Property Leasing

- Transportation Management

- Travel Management

- USA Services

- Vehicle Acquisition

- Vehicle Leasing

- Charge Card Services

14a. If “yes,” does this initiative address a weakness found during the PART review?	 Select “Yes” or “No” as applicable to the initiative.

14b.  If “yes,” what is the name of the PARTed program? Identify the name of the PART program that was assessed.

14c. If “yes,” what rating did the PART receive? Choose from the following selections as appropriate to the initiative

Effective		Moderately Effective		Adequate

Ineffective		Results Not Demonstrated

15. Is this initiative for information technology?  “Yes” is the appropriate answer to this question. Information technology, as defined by the Clinger-Cohen Act of 1996, sections 5002, 5141, and 5142, refers to any equipment or interconnected system or subsystem of equipment that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information.  For purposes of this definition, equipment is “used” by an agency whether the agency uses the equipment directly or it is used by a contractor under a contract with the agency that (1) requires the use of such equipment or (2) requires the use, to a significant extent, of such equipment in the performance of a service or the furnishing of a product.  Information technology includes computers, ancillary equipment, software, firmware and similar procedures, services (including support services), and related resources.  See Section 53 for additional information.

Figure 8: Screening Questions BY09

\

16. Percentage of IT Initiative that is dedicated to a COTS product:  GSA initiative owners must identify the estimated percentage of the IT initiative’s budget that is dedicated to a Commercial-off-the-Shelf (COTS) product licensing.  Initiative owners should report to the nearest whole number, or enter zero, if none.  This number should refer to the proposed funding for BY09. For questions related to COTS packages, please contact your OCIO liaison.

17. SAP/SAPI(s) Relationship: Identify to which SAP/SAPI(s) the initiative is related. For more information, please contact your OCIO liaison or OCFO point of contact.

18. Interdependencies with other initiatives: Initiative owners should indicate and describe the interdependencies among the initiative's components with each other and among other GSA and non-GSA initiatives. Items to include in this response may include the following:

- Whether the initiative has undergone a One GSA EA alignment

- Process and technical interdependencies between the initiative and other major initiatives (to include steady state initiatives)

- Initiatives that may be undergoing modifications

Note:  Initiative details described in the Interdependencies question will be for GSA internal use only and will not be transmitted to OMB.  Both major and non-major initiatives are required to fill in this field.

IT Screening Questions: If the initiative is for Information Technology, PMs will populate the questions found below.

Figure 9:  IT Screening Questions

19.  What is the level of the IT Project? (Per CIO Council PM Guidance):  OMB has noted that each major IT initiative and associated Project Manager (PM) must be assigned to one of three Project Management Levels that are designed to coincide with the project’s scope and the PM’s level of expertise.

Level 1: Manages a project within a division, bureau, or agency.

Level 2: Manages a cross-cutting project or agency-wide system integration across GSA.

Level 3: Manages a large, inter-governmental or government-wide complex, high risk IT project (e.g. E-Gov or PMA initiative, mission critical function, or high risk project).

For more information, please contact Janet Childs, GSA OCIO, (janet.childs@gsa.gov).

20. What project management qualifications does the Project Manager have? (Per CIO Council PM Guidance) IT Project Managers should achieve and demonstrate baseline skills in applicable competency areas, whether through on-the-job training, formal education and training or previous work experience. The PM’s skills and qualifications should be assessed to determine whether minimum project management requirements are being met.  Identify the project management qualifications of the PM.

(1)-The project manager assigned for this initiative has been validated as qualified in accordance with OMB PM Guidance.

(2)-The project manager assigned for this initiative is in the process of being validated as qualified in accordance with OMB PM Guidance.

(3)-The project manager assigned for this initiative is not validated as qualified in accordance with OMB PM Guidance.

(4)-The qualifications for the project manager named have been evaluated.

(5)-No project is currently assigned for this initiative.

(6)-N/A-This is not an IT initiative.

For more information, please contact Janet Childs, GSA OCIO, (janet.childs@gsa.gov).

OMB typically reviews Project Management as part of their 300 assessment. To perform well in this area, the level of the initiative must be compliant with the Federal CIO Council Guidance, the PM must be validated as qualified for this initiative via FAC –P/PM, and there must be successful completion and sound responses in other areas of the Exhibit 300, including Risk, Acquisition, Alternatives Analysis, Cost and Schedule, and Performance Tables.

21. Is this initiative or any project(s) within this initiative identified as “high risk” on the Q4 – FY 20076 agency high risk report (per OMB’s Memorandum M-05-23 “high risk” memo)?  Select “Yes” or “No” as appropriate for the initiative.

FY 2007 High risk initiatives/projects at GSA include:

- E-Travel

- E-Authentication

- Integration Acquisition Environment

- USA Services

- Federal Asset Sales

- FM LOB

- IOI LOB

- PAR (ePayroll)

- GSA FMLOB COE/Pegasys

- CHRIS-EHRI

- E-Authentication Migration

- Business Gateway - Forms.gov

- FAS Sales Center SSP (RP)

- FAS Sales Center SSP (PP)

- IAE SSP (FedBizOps)

- IAE SSP (EPLS)

- IAE SSP (FPDS-NG)

- EHRI Migration

- HRLOB Migration

High risk initiatives, as described by OMB, are those initiatives that require special attention from oversight authorities and senior levels of agency management.  OMB guidance states that an initiative should be designated as high risk when it meets the following criteria:

- The agency has not consistently demonstrated the ability to manage complex projects;

- The project has exceptionally high development, operating, or maintenance costs, either in absolute terms or as a percentage of the agency’s total IT portfolio;

- The project is correcting recognized deficiencies in the adequate performance of an essential mission program or function of the agency, a component of the agency, or another organization; or

- A delay or failure of a particular project would introduce an unacceptable or inadequate performance or failure of an essential mission function of the agency, a component of the agency, or another organization.

- The initiative is an E-Gov or a LoB initiative managed by the agency.

All initiatives associated with migrations to an E-Gov or LoB initiative are also considered high risk until migration is completed or OMB has determined it is no longer applicably designated as high risk.

22. Is this a financial management system? Select “Yes” or “No” as appropriate for the initiative.

A financial system is comprised of systems or applications that are used to collect, process, transmit, or maintain data about financial events; support preparation of financial statements, financial planning or budgeting activities; or accumulate and report cost information. OMB considers all financial systems with an annual cost over $500,000 to be a major system requiring an Exhibit 300.  The Federal Financial Managers Integrity Act (FFMIA) establishes requirements for management controls, evaluations, and reports related to the financial integrity of federal programs.

22a. If “yes,” does this initiative address a FFMIA compliance area? Select “Yes” or “No” as appropriate for the initiative.

1.	 If “yes,” which compliance area? If applicable, document the appropriate FFMIA compliance area (250 character limit)

2.	 If “no,” what does it address? Otherwise, document what the financial management system addresses (500 character limit).

22b.	If “yes,” please identify the system name(s) and system acronym(s) as reported in the most recent financial systems inventory update required by Circular A–11 Section 52. Provide the system name(s) and acronym(s) that are part of the financial management system initiative.

22c. Provide the Percentage Financial Management for the budget year. GSA initiative owners must identify the estimated percentage of the total system budget authority associated with the financial components (excluding information on budget formulation and execution activities, which are now captured separately). Initiative owners should report to the nearest whole percent, or enter zero, if none. For more details, refer to the financial system definition in OMB A-11 section 53.4  For questions with Percentage Financial, please contact the OCIO or your SSO Controller.

23. What is the percentage breakout for the total Budget Year (BY) funding request for the following? (This should total 100%)

23a. For budget year, what percentage of the total initiative is for hardware?

23b. For budget year, what percentage of the total initiative is for software?

23c. For budget year, what percentage of the total initiative is for services?

23d. For budget year, what percentage of the total initiative is for other services?

Breakout the percentage of funding you are requesting for expenditures on hardware, software, services, and other areas in BY 2009.  The total percentage of funding must add up to 100%.  For example:

Hardware- 20%

Software- 30%

Services- 40%

Other- 10%

Total- 100%

24. If this is project produces information dissemination products for the public, are these products published to the Internet in conformance with OMB Memorandum 05-04 and included in your agency inventory, schedule, and priorities?

The functions required under 05-04 include:

- Establish and Maintain Information Dissemination Product Inventories, Priorities, and Schedules OMB Circular A-130 E-Gov Act of 2002 (Section 207)

- Ensure Information Quality Information Quality Act Section 515 of the Treasury Appropriations Act

- Establish and Enforce Agency-wide Linking Policies E-Gov Act of 2002 (Section 7) No Fear Act of 2002 Small Business Paperwork Relief Act of 2002

- Communicate with the Public and with State and Local Governments OMB Circular A-130 Paperwork Reduction Act

- Search Public Websites  OMB Circular A-130 (Section 8)

- Use Approved Domains GSA Domain Name Policy

- Implement Security Controls OMB Circular A-130, Appendix III OMB memorandum M-04-25 E-Gov Act of 2002, Section 207(f)(1)(b)(iv)

- Protect Privacy OMB Circular A-130 Appendix I OMB memorandum M-03-22 Children's Online Privacy Protection Act of 1998 (COPPA) E-Government Act of 2002, Section 207(f)(1)(B) Privacy Act of 1974

- Maintain Accessibility Section 508 of the Rehabilitation Act (29 U.S.C. 794d) Department of Justice guidance for Executive Order 13166

- Manage Records Code of Federal Regulations (CFR), Parts 1220-1238 E-Gov Act of 2002, Section 207(e), Public Access to Electronic Information NARA Guidance on Managing Web Records

25.	Contact information of individual responsible for privacy related questions:	 Indicate the point of contact for the individual responsible for privacy information. For more information, please contact Kim Mott, GSA OCHOC, kim.mott@gsa.gov, 202-209-1317).

26.	Are the records produced by this initiative appropriately scheduled with the National Archives and Records Administration’s approval?Choose “Yes” or “No” to indicate whether the initiative is appropriately scheduled with the National Archives and Records Administration.

Records schedule refers to:

(a) An SF 115, Request for Records Disposition Authority, that has been approved by NARA to authorize the disposition of Federal records;

(b) A General Records Schedule (GRS) issued by NARA; or

(c) A printed agency manual or directive containing the records descriptions and disposition instructions approved by NARA on one or more SF 115s or issued by NARA in the GRS. (See also the definition Comprehensive schedule.)

For more information, please contact Marc Wolfe, GSA OCIO, (marc.wolfe@gsa.gov).

###### GAO High Risk Areas BY09

This is a new question for FY09 and must be answered by ALL initiatives.

Figure 10: GAO High Risk Areas

27. Does this initiative directly support one of the GAO High Risk Areas? Select “Yes” or “No” as applicable to your investment The complete list of GAO’s 2007 High Risk Areas can be found at http://www.gao.gov/new.items/d07310.pdf. The 2007 High Risk Areas include:

- Addressing Challenges in Broad-based Transformations

- Strategic Human Capital Management

- Managing Federal Real Property

- Protecting the Federal Government’s Information Systems and the Nation’s Critical Infrastructures

- Implementing and Transforming the Department of Homeland

- Establishing Appropriate and Effective Information-Sharing Mechanisms to Improve Homeland Security

- DOD Approach to Business Transformation

  - DOD Business Systems Modernization

  - DOD Personnel Security Clearance Program

  - DOD Support Infrastructure Management

  - DOD Financial Management

  - DOD Supply Chain Management

  - DOD Weapon Systems Acquisition

- FAA Air Traffic Control Modernization

- Financing the Nation’s Transportation System

- Ensuring the Effective Protection of Technologies Critical to US National Security Interests

- Managing Federal Contracting More Effectively

- DOD Contract Management

- DOE Contract Management

- NASA Contract Management

- Management of Interagency Contracting

- Assessing the Efficiency and Effectiveness of Tax Law Administration

- Enforcement of Tax Laws

- IRS Business Systems Modernization

- Modernizing and Safeguarding Insurance and Benefit Programs

- Modernizing Federal Disability Programs

- Pension Benefit Guaranty Corporation Single-Employer Pension Insurance Program

- Medicare Program

- Medicaid Program

- National Flood Insurance Program

### Part I.B:  Summary of Spending BY09

Costs in this table should be consistent with the Cost & Schedule Performance section, as well as the Acquisition/Contracts section. This section should show that the project is well-planned throughout its lifecycle. All cost data should be entered into eCPIC in thousands. Exported data will be converted into millions. Costs in the Summary of Spending and Cost and Schedule Performance Section should be consistent.  This section should demonstrate that the project is well planned (e.g., appropriate mix of Planning, Full Acquisition, and Maintenance costs) and likely to come in on budget. The Summary of Spending section identifies the required budget authority to fund the initiative in inflated dollars. The figure below provides an illustrative example of the Summary of Spending Table.

Note: The user must first “update data grid values” prior to “save” in order to save all data.

Figure 11: Summary of Spending Screenshot

Note: For the cross-agency initiatives, this table should include all funding (both managing partner and partner agencies).

Planning: costs required for upfront planning for new initiatives and changes or modifications to existing initiatives to improve capability or performance.  This may include the personnel or direct costs required to identify strategies and alternatives for solving a problem, developing initial plans, conducting studies, and etc.

Acquisition: specific products and services that are being acquired for the initiative.  This may include contractor services, hardware, software, telecommunications, and etc.

Operations & Maintenance: costs at current capability and performance level, including costs for personnel, maintenance of existing initiatives, corrective software maintenance, voice and data communications maintenance, and replacement of broken IT equipment. Operations & Maintenance dollars are used for recurring expenses, including the cost for running the current system, etc. All costs associated with maintaining the system, e.g., technology refresh, minor upgrades, etc. should be included under Maintenance dollars.

All Spending estimates should be provided through the Project Planned Completion Date.

Government FTE Costs should not be included as part of the TOTAL represented. Government FTE costs appear below the Total, Sum of All Stages Line in the Summary of Spending Table.

Note: All costs in the Summary of Spending Table and Funding Sources Table must be validated by the initiative owners with the appropriate SSO Controllers or OCFO Point of Contact as applicable. For a list of appropriate contacts, see Appendix D.

Government FTE Costs: Government FTE Costs should not be included as part of the TOTAL represented. Government FTE costs appear below the Total, Sum of All Stages Line in the Summary of Spending Table (Refer to Figure 10).

Average annual salary at GSA is currently approximately equivalent to a GS-13-01 ($79,397per annum).  OMB A-11 guidance states that the fringe benefit to use when estimating FTE costs associated with IT initiatives should be 32.8%.  Based on this the estimated cost per FTE would be approximately $105,439 per annum at GSA. This is general guidance and should be customized by initiative.

Future years should compensate for inflation using the guidance outlined in OMB Circular A-94. For example, the inflation rate for ten year projections would 2.2% (Calculation based on OMB Circular A-94- 10 year nominal interest rate of 5% MINUS ten-year real interest rate of 2.8%).

All amounts represent budget authority in millions, and are rounded to three decimal places.  Federal personnel costs should be included only in the row designated “Government FTE Cost,” and should be excluded from the amounts shown for “Planning”, “Full Acquisition,” and “Operations & Maintenance.”  The cost of the Government FTEs should not be included in the “Total all Stages” line item.” Number of FTE Represented by Cost” should be the number of Government FTEs identified in the Government FTE costs.

Full Time Equivalents BY09: Use the table on the following page to provide the number of Government Full Time Equivalents (FTE) represented by the Government FTE Costs in the Summary of Spending Table. Numbers should be entered in decimal format for each of the categories listed.

Initiative owners should enter the number of FTEs dedicated to particular tasks, including Financial Management, Security, Program Management, and Other.

- Financial management activity refers to financial systems and the financial portion of mixed systems that support the interrelationships and interdependencies between budget, cost, and management functions, and the information associated with business activities.

- Security refers to activities related to security controls and requirements for systems, certifying and accrediting systems, and other activities related to the Federal Information Security Management Act and OMB security policies, etc.

- Program Management refers to activities related to managing a project and/or portfolio of projects. Program Management will also include project management activities.  Information Technology activity, as defined by the Clinger-Cohen Act of 1996, refers to any equipment or interconnected system or subsystem of equipment used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission, or reception of data or information.

- Other activities refer to all other activities that can not be categorized as financial management, security, or program management. The total category is the sum of all of the data and is the only row of data in this table that will be submitted to OMB directly.

The Government FTE table should align with the Government FTE costs in the Summary of Spending table. Initiative Owners should calculate this data for prior years, if possible

See the figure below for an illustrative example of the FTE Table.

Figure 12: Full-Time Equivalents

*This row represents the 'Number of FTE represented by cost' from Summary of Spending table and will be sent to OMB.

Funding Sources BY09:  Funding sources are any budgetary resources used to fund an IT initiative. For Exhibit 53 reporting in eCPIC, initiative owners must select each funding source applicable for their initiatives and break-out the associated cost data by DME, SS, and Total funding. Initiative owners should add as many funding source line items, as appropriate.

In accordance with OMB requirements, each funding source that is applicable for an initiative must have an associated MAX account code, as designated from the Department of Treasury. As a result of this requirement, GSA renamed all funding sources prior to the BY08 submission that were previously in eCPIC to match the Department of Treasury MAX Account names and codes. This allowed each investment to show clear alignment of their respective funding sources and MAX accounts.

Where a GSA funding source in eCPIC could be mapped to a MAX account, the funding source name was updated in eCPIC. Where a funding source name could not be mapped to a MAX account, it was de-activated in eCPIC. Appendix E contains a mapping of GSA’s funding sources from eCPIC to the MAX account names and codes. This appendix also illustrates de-activated funding sources, as well as new funding sources and their respective MAX account codes. An illustrative example of the Funding Source table is included below for reference. See the figure below for an illustrative example of the Funding Sources Table.

Figure 13: Funding Sources Table

It is the responsibility of each initiative owner and/or their points of contact to validate the funding source information in Appendix E.

For questions with the funding source table or budget data, initiative owners should work with their SSO Controller or OCFO point of contact as applicable. These points of contact are available in Appendix D.

As initiative owners are updating their funding source information in the Exhibit 300, they must select whether or not to include funding sources in the Exhibit 53. All GSA-specific funding should be “checked” or included in the Exhibit 53. (See highlighted area in Figure 11 above.) E-Gov/LoB initiatives, where GSA is a managing partner, will want at least one line for other agency contribution.  That line should be “unchecked” or deselected for inclusion in the Exhibit 53. There are 5 categories listed for other agency contributions, including:

- General Activities (Working Capital Fund – Other Agency)

- Supply and Technology Activities (Acquisition Services Fund/ASF – Other Agency)

- Supply and Technology Activities (General Supply Fund/GSF – Other Agency)

- Supply and Technology Activities (Information Technology Fund/ITF – Other Agency)

- Real Property Activities (Federal Buildings Fund/FBF – Other Agency)

The 53 should reflect GSA funding only while the Exhibit 300 Summary of Spending and Funding Sources table will include GSA and other agency funding. The screenshot below denotes the line which must be selected in order for a funding source to be included in the Exhibit 53.

Additionally, in the “Funding Source Type” drop-down menu, GSA has deactivated the choices available in previous years. All necessary data needed for collection will be categorized through the use of Max Accounts in the “Funding Source Name” drop-down menu.  Users should select the only option available from the drop down menu, which is listed as “funding.”

Balancing the Funding Sources Table to the Summary of Spending Table:  Prior to finalizing the funding updates in eCPIC, the initiative owner should validate that the Summary of Spending table matches the Funding Sources table. All funds should be accounted for in both tables so they equal each other in the proper DME/SS classifications, as well as in the appropriate year.

For example, if an initiative’s Summary of Spending table shows $225,000 for CY08 DME ($150,000 + 75,000 in Govt. FTE costs) and $125,000 for CY08 SS ($75,000+ $50,000 in Govt. FTE costs), then the initiative owner should then ensure that these costs are accurately accounted for under the CY08 DME and SS rows in the Funding Sources Table, even if they are spread among multiple funding sources. This exercise is particularly important for the PY, CY, and BY data.

Balancing these calculations correctly will ensure that the Agency submits an accurate Exhibit 53 to OMB.  Additionally, cross-agency initiatives must ensure that agency vs. other agency funding is appropriately accounted for and matches within both tables. The eCPIC tool has functionality to verify whether initiative owners have accurately accounted for costs. In the Funding Sources table, click the icon highlighted in figure below:

Figure 14: Initiative Totals and Balancing Tools Icon

Clicking this icon launches a tool called the Initiative Financial Totals and Balance Table, as seen in the figure on the next page. This table cross-checks the Summary of Spending and Funding Sources data to determine whether the costs balance. As seen below, the BY09 data differs by $25,000, revealing that the Funding Sources data needs to be re-examined for accuracy. Once balanced, the table will show a zero balance for all budget years.

Figure 15:  Initiative Financial Totals and Balancing Table

Funding Questions BY09: The information for Project Managers to capture in the Funding Questions area of eCPIC is illustrated in the eCPIC screenshot below:

Figure 16: Funding Questions BY09

Select “Yes” or “No” as applicable to the initiative. If “yes,”? Provide the number of additional FTEs and the year/number that will be required. In addition, if the Exhibit’s summary of spending has changed from the FY2008 President’s budget request, explain those changes and identify the reasons for the changes.

Percentage Budget Formulation (BF): For each line item in the Exhibit 53, GSA initiative owners should report the estimated % of total IT initiative funding that is associated with Budget Formulation. Budget Formulation represents activities undertaken to determine priorities for future spending and to develop an itemized forecast of future funding and expenditures during a targeted period of time. This includes the collection and use of performance information to assess the effectiveness of programs and develop budget priorities. For questions with Percentage BF, please contact your OCIO liaison.

Percentage Budget Execution (BE): For each line item in the Exhibit 53, GSA initiative owners should report the estimated % of the total IT initiative  funding that is associated with Budget Execution. Budget Execution represents activities associated with the legal and managerial uses of budgetary resources to achieve results that comply with the enacted budget and Administration policy. Budget execution activities include but are not limited to: apportionments, allotments, commitments, reprogramming actions, incurring obligations, and funds control. For questions with Percentage BE, please contact your OCIO liaison.

### Part I.C Acquisition/Contract Strategy BY09

Initiative owners must fill out the table seen in the figure below, for all contracts and/or task orders (including all non-Federal) that are currently in place or planned for this initiative. OMB requires a strong acquisition strategy that mitigates risk to the Federal Government, accommodates Section 508 as needed, and uses performance-based contract statements of work (SOWs).

When possible, the acquisition strategy costs should align with data provided in the Summary of Spending table. Please include current contracts, as well as contracts that you are aware of that may not yet have been awarded. The acquisition strategy refers to the process of deciding which initiative/project needs are better satisfied by external sources and the process for acquiring those needs in the most cost effective way.  Major initiatives should rely on the advice of contracting/procurement officials.

In order to provide a sound response to contract/acquisition questions, initiative owners should (1) ensure that all questions are answered and complete within the Contracts Table; (2) answer yes (as applicable) to the following: (a) competitively awarded; (b) performance-based; (c) EVM in contract or provided valid explanation on why not; (d) contains security and privacy clauses; (e) ensures 508 compliance - or provided valid N/A response; and (f) approved acquisition plan in place; (3) ensure that the CO has been certified to the appropriate level; and (4) supply the Acquisition Plan date. Additionally, the initiative should be aligned with other relevant Exhibit 300 sections, including the Summary of Spending and Performance Baseline Tables.

Figure 17: Contracts/Task Order Table BY09

Contract or Task Order Number: Provide the contract or task order number for the contract.

Type of Contract/Task Order: Indicate the type of contractual vehicle that is being used to procure the product/service.  For example, typical contract vehicles, and associated characteristics, include:

Cost Reimbursable

- Government pays actual cost (labor, purchases, travel, etc.) to the contractor plus some pre-set fee (profit)

- Cost is estimated up front to set a ceiling amount of liability

- Contractor must maintain a certified cost accounting system (certified and monitored by a Government Audit Agency)

- May not be used for “commercial items”

Fixed Price

- Government pays a fixed price-per-unit, which includes the Contractor’s costs and profit/loss.  The “unit” being purchased varies dramatically:

  - The final system

  - Production units, e.g., “desktop computers”

  - Service units, e.g., “user seat licenses”

  - Labor hours

- Prescribed by the Federal Acquisition Regulation for “commercial” items

Variations are often built around these two contract vehicles (e.g., firmed fixed price, fixed price incentive, time and materials, cost sharing, cost plus award fee, etc.).

Has the contract been awarded, if so what is the date of the award? If not, what is the planned award date?: List the date that the contract has been awarded.  If the contract has not been awarded, list the planned award date.

Start and end date of Contract/Task order: List the start and end date of the Contract/Task order.

Total Value of Contract/Task Order: Identify the total value of the Contract/Task order in millions. When specifying cost, please identify only the costs applicable to the initiative. For example, if a task order supports project management for multiple initiatives, estimate cost associated with that initiative only.

Is this an Interagency Acquisition? Answer this question “Yes” or “No”. An interagency acquisition would refer to an agency’s acquisition on behalf of another agency. For example, GSA’s Federal Acquisition Service conducting an acquisition for the Department of Homeland Security (DHS) is an example of an interagency acquisition.

Is it performance based? Answer this question “Yes” or “No”. A performance-based contract is a contract in which specific units of service have specific costs and the grantee is reimbursed for funds expended on the number of units performed within a certain time period. OMB endorses a seven-step methodology for performance-based contracting which includes the following:

- Establish an integrated solutions team

- Describe the problem that needs solving

- Examine private-sector and public-sector solutions

- Develop a performance work statement (PWS) or statement of objectives (SOO)

- Decide how to measure and manage performance

- Select the right contractor

- Manage performance

Competitively awarded? Answer this question “Yes” or “No”.  Take into consideration the competition process that was used in the final selection (i.e. number of competitors assessed, qualifications or experience that was reviewed when selecting the contractors, methodology used to select the contractor, and etc.).

What, if any, alternative financing option is being used (ESPC, UESC, EUL, N/A): Answer this question “Yes” or “No”. Most GSA initiatives will respond “N/A” or Not Applicable. However, definitions include the following:  Energy savings performance contract (ESPC) means a contract providing for the performance of services for the design, acquisition, financing, installation, testing, operation, and, where appropriate, maintenance and repair of an identified energy or water conservation measure or series of measures at one or more locations. See E.O. 13123 and the Federal Acquisition Regulation.  Utility energy efficiency service contract (UESC) means a local utility providing up-front project funding and Federal agencies pay for the services over time, either on their utility bill, or through a separate demand-side management agreement. See FAR Part 41 for more information.  Enhanced Use Leasing (EUL) allows agencies to invest underutilized agency land, buildings, and other resources, to improve services, provide needed facilities, or generate new resources.

Is EVM in the contract? Answer this question “Yes” or “No”.  (Earned Value Management (EVM) is a project (initiative) management tool effectively integrating the initiative scope of work with schedule and cost elements for optimum initiative planning and control.) Indicate whether or not EVM requirements are included in the contract.

Does the contract include the required security & privacy clauses? Answer this question “Yes” or “No”.  Consider both GSA and federal security and privacy regulation in your answer.

Name of Contracting Officer (CO) contact information:  Identify the name of the contracting officer and phone number/email address.

CO Certification Level: Identify the CO’s Certification Level (i.e., Level 1,2, or 3) or N/A for Not Applicable.

If N/A, has the agency determined the CO assigned has the competencies and skills necessary to support this acquisition?  Answer this question “Yes” or “No”.

Contracts/Task Order Questions BY09:  IT initiative owners must also answer the questions listed in Figure 16 below:

Figure 18:  Contracts/Task Order Questions BY09

28. If earned value is not required or will not be a contract requirement for any of the contracts or task orders above, explain why: If EVM is not a contract requirement, provide an explanation here.

29. Do the contracts ensure Section 508 compliance? Answer “Yes”, “No” or N/A here and explain why or how. Section 508 of the Rehabilitation Act of 1973 (29 U.S.C. 794d) requires Federal agencies to develop, procure, maintain, or use electronic and information technology that is accessible to Federal employees and members of the public with disabilities.  Indicate whether or not the initiative adheres to Section 508. We encourage you to work with your contracting officer to verify if your contracts are compliant.

30. Is there an acquisition plan which has been approved in accordance with agency requirements?	Provide a response regarding whether or not an acquisition plan has been approved. Provide applicable dates or an explanation.

### Part I.D Performance Information BY09

GSA initiative owners must use the Federal Enterprise Architecture (FEA) Performance Reference Model (PRM) to report performance goals and measures . Major IT initiative owners must map all Measurement Indicators to the corresponding Measurement Area and Measurement Grouping identified in the PRM.  There should be at least one Measurement Indicator for each of the four different Measurement Areas (for each fiscal year).  The PRM is available at http://www.whitehouse.gov/omb/egov/a-2-prm.html  The table can be extended to include performance measures for years beyond FY 2009.

In order to be assessed well in this area, initiative owners must provide (1) performance measures that are outcome-based and are stated as measures (e.g., Number of…, % of…, etc.) with the direction, e.g. increasing, decreasing, clearly identified; (2) four PRM outcome-oriented performance goals listed for each measurement area for at least three years (07, 08, and 09); (3) measurement indicators, baselines, targets, and actual results that show quantifiable data with an incremental improvement over time; and (4) actual results provided for 06 and at least partial results for 07.  Additionally, these measures should be consistent with other measures provided to OMB (e.g., PART).

Figure 19: Performance Information BY09

Identify the outcomes and outputs that the initiative supports. Include the anticipated improvement measures for the initiative/project.  At least one performance measure needs to be identified for each year for each of the four measurement areas (e.g. one for mission and business results, one for customer results, etc).  Accurate baselines should be identified and documented.  This table is used to measure the progress and success of the activity through its life cycle.

Measurement Area:  The PRM defines four areas for measuring performance that must be addressed for each fiscal year.  The following information is defined by the FEA PRM.

- Mission and Business Results:  Captures outputs that agencies seek to achieve; results will align with program office performance objectives.

- Customer Results:  Captures how well the agency or process within the agency serves its customers (ultimately citizens); results should refer to the most external customer the initiative supports.

- Processes and Activities: Captures outputs directly resulting from the processes or activities the initiative supports.

- Technology:  Captures key elements of performance directly relating to the IT initiative (including applications, infrastructure, or services provided to support a process or program).

Measurement Category: Corresponds to each Measurement Area. Details can be accessed on the FEA website.

Measurement Indicator:  Identifies the type of metric that will be used to monitor the initiative’s performance.

Baseline: For each fiscal year, provide the existing performance level for the identified goal or measure (e.g., FY 2006 response time average = 2 hours.).

Planned Improvement to the Baseline: Briefly describe the planned improvement in performance (e.g., 50% reduction in response time.).

Actual Results: Report the actual performance metric result for the fiscal year (e.g., FY 2007 response time average was reduced from 2 hours to 1 hour). Year-end data is required when available.  It may include partial year data during the current performance year if full-year data is not available.

### Part I.E Security and Privacy BY09

Respond to the questions seen in the figure below and verify the system owner took the following actions.

In this section, initiatives must demonstrate that:

- Costs of security controls are understood & explicitly incorporated into life-cycle planning.

- Security controls are consistent with and an integral part of the EA.

- Specific methods are used to ensure that the security controls are commensurate with the risk and magnitude of harm that may result from the loss, misuse, or unauthorized access to or modification of the system itself or the information it manages.

According to OMB Circular A-130, agencies must do or demonstrate the following:

- Develop an agency information security program consistent with NIST guidance

- Identify additional security controls necessary to minimize risk to & potential loss from systems that promote/permit public access, other externally accessible systems & systems interconnected with systems over which program officials have little or no control

- Deploy effective security controls & authentication tools

- Ensure that the handling of personal information is consistent with relevant policies

- Document agency standards/guidance more stringent than those promulgated by NIST

For more information, please contact John Kurpiel (john.kurpiel@gsa.gov) for Information Assurance (IA)/Security issues and Kim Mott (kim.mott@gsa.gov) for Privacy issues.

Figure 20: Costs & Risks BY09

31. Have the IT security costs for the system(s) been identified and integrated into the overall costs of the initiative: Indicate whether or not the initiative has included the IT security costs for each of the individual systems that comprise the initiative (and are listed in the tables below) and whether or not the costs have been integrated into the overall cost of the initiative.

31a.  If the IT security costs have been identified for the initiative, identify the percentage of total BY2009 funding that will be used to fund IT security.  This should be determined by dividing total BY2009 IT security costs by the total BY2009 funding request.  The percentage should be reported in whole numbers plus two decimals.

32. Is identifying and assessing security and privacy risks a part of the overall risk management effort for each system supporting or part of this initiative: Note whether or not risk management activities include security and privacy risks. Risk management plans at GSA should incorporate security and privacy risks and, if this is the case, “Yes” is the appropriate response.

33. Percent Internet Protocol version 6 (IPv6)

Completing this field is a new requirement for the Exhibit 53.  GSA initiative owners must identify the estimated percentage of the total IT initiative budget authority associated with the agency’s IPv6 implementation. Initiative owners should report to the nearest whole percent, or enter zero, if none.   This number should refer to the proposed funding for BY09. For questions with percent IPv6, please contact your OCIO liaison.

34. Percentage Homeland Security Presidential Directive-12 (HSPD-12)

Completing this field is a new requirement for the Exhibit 53.  GSA initiative owners must identify the estimated percentage of the total IT budget authority associated with the agency’s HSPD-12 implementation.  Initiative owners should report to the nearest whole percent, or enter zero, if none. This number should refer to the actual funding for CY07. For questions with Percent HSPD-12, please contact your OCIO liaison.

35. Security: Systems in Planning (and Undergoing Enhancement(s), Development, and/or Modernization)

The table in Figure 20 should be used to provide security information for all systems that comprise the larger initiative that are in the planning phase. This should only include the systems that are still in development (i.e., requesting “Planning” and “Acquisition” funding in the Summary of Spending table) and are not yet operational.  The systems that are identified in this table should also be included in the Privacy table in Figure 22).

Note that if the initiative shows DME funding in the Summary of Spending Table, the Systems in Planning Security Table must be completed. All dates in this table should be posted as future dates. The planned C&A date in this table must occur prior to the planned operational date.

Figure 21:  Security: Planning Systems BY09

All systems should align to the FISMA inventory. When filling out this table, please refer to the FISMA inventory to identify how (i.e., “planning” or “operational”) you should report the initiative’s systems.

36. Security:  Operational Systems BY09

The table in Figure 22 should be used to provide security information for all systems that comprise the larger initiative that are in the operational/steady state maintenance phase.  This should only include the systems that are requesting “Operations and Maintenance” funding in the Summary of Spending table. The systems that are identified in this table should also be included in the Privacy table in Figure 24).

Figure 22:  Security: Operational Systems

Note: NIST FIPS refers to the National Institute for Standards and Technology Federal Information Processing Standards

Has C&A been Completed using NIST 800-3: Identify whether a C&A has been completed on this system using NIST 800-37

Date Completed C&A: Identify the completion date for Certification and Accreditation of the system. Note that C&A dates are considered current within three years prior the BY09 submission date (September 10, 2007)

What standards were used for the Security Controls Tests?  Identify standards used for the security controls test.

Date Complete(d): Security Control Testing:  Identify the completion date for the security controls test. Control testing must be completed within one year prior to OMB BY submission for all operational systems

Date the contingency plan tested: Identify the completion date for testing for the contingency plan. The contingency plan date is considered current if it is within one year prior to OMB BY submission for all operational systems

Security: Weaknesses & Contractor Procedures:

Major IT initiative owners must populate the information illustrated in Figure 23 as the final data call in the Security Component of the BY09 Exhibit 300.

Figure 23:  Security: Weaknesses & Contractor Procedures

37. Have any weaknesses, not yet remediated, related to any of the systems part of or supporting this initiative been identified by the agency or IG?  Identify whether or not the IG has reported weakness for part or all of this initiative

37a. If “yes,” have those weaknesses been incorporated into the agency’s plan of action and milestone process?  If “Yes”, indicate whether or not GSA has addressed these weaknesses in a plan of action and milestone process.

38. Indicate whether an increase in IT security funding is requested to remediate IT security weaknesses  Indicate whether or not IT security funding has been increased to remediate IT security weaknesses.

38a. If “yes,” specify the amount, provide a general description of the weakness, and explain how the funding request will remediate the weakness: If “Yes”, indicate an amount and provide a description of the weakness, as well as how the funding will address it. This discussion should include a description of any planning, implementation and monitoring activities that will  be required to address the identified weakness.

39. How are contractor security procedures monitored, verified, and validated by the agency for the contractor systems above? For contractor-operated systems, as identified in Questions 3 & 4, describe GSA’s process for monitoring, verifying, and validating the contractor security procedures. This response should include a description of the processes, whether or not contractors are on-site or at their own facility, whether a status report is submitted, whether a non-disclosure agreement is signed, and how security procedures are monitored by GSA. Ensure that this response is detailed, and specific to the initiative.

40. Planning & Operational Systems – Privacy Table

Major IT initiative owners must provide the information shown in Figure 22 for all systems that are identified in the Security tables (both Planning and Operational)

Figure 24: Privacy: Planning and Operational Systems BY09

Name of System: Identify the name of the system

Is this a new system? Answer ”Yes” or no regarding whether or not the system is new.

Is there at least one Privacy Impact Assessment (PIA) which covers this system? Answer “Yes” or “No” as applicable to the initiative. Past justifications for “No” answers include the following:

- The system does not contain, process, or transmit personal identifying information.

- Even though the system has personal identifying information, the system contains information solely about federal employees and agency contractors.

Note that a PIA is required when a system involves, processes, stores, collects, or transmits data associated with members of the public (names, social security numbers, other unique identifiers).  However, whether or not a system processes data on individuals, it is important  to conduct a PIA from the planning and development/testing phases in order to ensure that if privacy issues are identified, the appropriate technological tools and procedures can be put in place to protect privacy

Note that all GSA systems are required to have a PIA due to Agency policy; however, only the initiatives that are listed on the GSA website are required by OMB to have a PIA. Therefore, the only initiatives that should answer “yes” to this question include:

- Business Information Solution (BIS)

- eLease

- Electronic Acquisition System (EAS)

- E-Travel Carlson Wagonlit Government Travel E2 Solutions (E-Travel E2 Solutions)

- E-Travel Electronic Data Systems FedTraveler.com (E-Travel FedTraveler)

- E-Travel Northrop Grumman Mission Solutions - GovTrip (E-Travel GovTrip)

- Excluded Parties (EPLS)

- Federal Acquisition Institute Online University Online University

- Federal Business Opportunities (FedBizOpps)

- Federal Procurement Data System - Next Generation (FPDS-NG)

- GSA Auctions (GSA Auctions)

- GSA jobs (GSA jobs)

- Office of Inspector General Information System (OIGMIS)

- Sales Automation System (SASy)

- System for Tracking and Administering Real-Property  (STAR)

For more information, please go to http://www.gsa.gov/Portal/gsa/ep/contentView.do?contentType=GSA_BASIC&contentId=21568&noc=T

Internet Link or Explanation (Medium Text): If the system has a PIA, provide the link(s) to the publicly posted PIA(s) with which this system is associated. Note: Links must be provided to specific documents not general privacy websites. If the system does not have a PIA, provide an explanation why the PIA has not been publicly posted or why the PIA has not been conducted.

Is a System of Records Notice (SORN) required for this system? Answer “Yes” or “No” as applicable to the initiative.

Whenever an agency establishes or changes a system of records, it must publish in the Federal Register a notice known as a System of Records Notice (SORN).

A System of Records Notice (SORN) refers to a statement providing to the public notice of the existence and character of a group of any records under the control of any agency from which information is retrieved by the name of the individual or by some identifying number, symbol, or other identifying particular assigned to the individual. The Privacy Act of 1974 requires this notice to be published in the Federal Register upon establishment or substantive revision of the system, and establishes what information about the system must be included.

Internet Link or Explanation (Medium Text):  If a SORN is required for the SORN, provide the link(s) to where the current and up to date SORN is published in the federal register.  Note: Links must be provided to specific documents not general privacy websites.  If no SORN is required or up to date, provide an explanation why the SORN has not been published or isn’t current.

For more information, please contact Marc Wolfe, GSA OCIO, (marc.wolfe@gsa.gov) or Kim Mott, GSA OCHCO, (kim.mott@gsa.gov).

System Breach Incidents: GSA requires its major IT initiative owners to fill out the following system breach information, as illustrated in the figure below

Figure 25:  System Breach Incidents

### Part I.F:  Enterprise Architecture BY09

In order to successfully address the Enterprise Architecture area of the capital asset plan and business case, the initiative must be included in the agency’s EA and CPIC processes, and mapped to the FEA. The business case must demonstrates the relationship between the initiative and the business, performance, data, services, application, and technology layers of the agency’s EA.

To perform well in this section, initiatives must (1) have a “business segment aligned” current and target architecture; (2) be included in the One GSA EA Transition Strategy & Sequence Plan; (3) demonstrate alignment to OMB FEA Reference Models; and (4) demonstrate alignment to and reuse of Government-wide initiatives such as those contained in published Federal Transition Framework.

Please contact Robert Seay, GSA OCIO, (robert.seay@gsa.gov), Enterprise Architecture, OCIO, for assistance with completing all EA sections of the BY09 Exhibit 300.

The General EA questions are illustrated in the figure below.

Figure 26: General EA Questions BY09

41. Is this initiative included in your agency’s target enterprise architecture?  Identify whether or not the initiative is a part of the GSA Target Enterprise Architecture.

41a. If “no,” please explain why?  If “No”, provide an explanation.

42. Is this initiative included in the agency’s EA Transition Strategy? Identify whether or not he initiative is a part of the GSA EA Transition Strategy

42a. If “yes,” provide the initiative name as identified in the Transition Strategy provided in the agency’s most recent annual EA Assessment.  If “Yes”, provide the initiative name

42b.  If “no,” please explain why? If “No”, provide an explanation.

43. Is this initiative identified in a completed (contains a target architecture) and approved segment architecture?  Identify whether the initiative is identified in a complete and approved segment architecture.

43a. If “yes,” provide the name of the segment architecture as provided in the agency’s most recent annual EA Assessment. Provide the name of the segment architecture in which the initiative is identified.

Figure 27: General EA Questions BY09

44.  Identify Segment Architecture: Identify whether or not the initiative is identified in a completed (contains a target architecture) and approved segment architecture.

44a. If “yes,” provide the name of the segment architecture.  If “no,” provide an explanation.

Please contact Robert Seay (robert.seay@gsa.gov) of GSA’s Enterprise Architecture office if you have any additional questions.

45.  Segment Architecture:  Completing this field is a new requirement for the Exhibit 53.  GSA Initiative owners should include the status of the initiative’s alignment to the agency’s segment architecture process.  The following options are available:

1.	This initiative is identified as supporting an approved, complete segment architecture.

2.	This initiative is part of an incomplete or in-process segment architecture.

3.	This initiative is part of a planned, but not yet to be initiated, segment architecture.

Please contact Robert Seay (robert.seay@gsa.gov) of GSA’s Enterprise Architecture office if you have any additional questions.

FEA Service Component Reference Model: In the figure below, identify the service components funded by this major IT initiative (e.g., knowledge management, content management, customer relationship management, etc.).For detailed guidance regarding components, please refer to http://www.whitehouse.gov/omb/egov/a-4-srm.html.

Figure 28:  FEA SRM

Agency Component Name:  Indicate the name of the service component as funded by the initiative.

Agency Component Description:  Provide a description of the service component.

Service Domain: Select the SRM Service Domain that is the related to the Service Component, as defined in the FEA mappings.

FEA SRM Service Type:  Select the “SRM Service Type” that is related to the Service Component, as defined in the FEA mappings.

FEA SRM Component:  Selecting the appropriate SRM Component, using existing Components or identifying as “NEW”. A “NEW” component is one not already identified as a service component in the FEA SRM.

FEA Service Component Reused Name:  Identify the name of reused components, which refers to components being funded by another initiative but being used for this initiative. A reused component is one being funded by another initiative, but being used by this initiative.  Rather than answer “Yes” or “No”, identify the reused service component funded by the other initiative and identify the other initiative using the Unique Project Identifier (UPI) code from the OMB Ex 300 or Ex 53 submission.

FEA Service Component Reused UPI:  Identify the UPI  # of the other initiative funding the reused component.

Internal or External Reuse? Indicate whether the reused is internal or external. Internal’ reuse is within an agency.  For example, one agency within a department is reusing a service component provided by another agency within the same department.  ‘External’ reuse is one agency within a department.  A good example of this is an E-Gov initiative service being reused by multiple organizations across the federal government.

BY Funding Percentage :  Provide the BY09 % of funding requested by each component.  If external, provide the BY09% requested funding amount transferred to another agency to pay for the service.  The percentages in this column can, but are not required to, add up to 100%.

FEA Technical Reference Model (TRM): Major IT initiatives will use this table, as illustrated in Figure 29, to demonstrate how this major IT initiative aligns with the FEA Technical Reference Model (TRM). Initiative owners must  list the Service Areas, Categories, Standards, and Service Specifications supporting their IT initiatives.

Figure 29:  FEA TRM BY09

FEA SRM Component  Service Components identified in the previous question should be entered in this column. Please enter multiple rows for FEA SRM Components supported by multiple TRM Service Specifications.

FEA TRM Service Area:  Select the “TRM Service Area” that relates to the identified “SRM Component.

FEA TRM Service Category   Select the “TRM Service Category” that relates to the identified “SRM Component,” as defined according to the FEA mappings.

FEA TRM Service Standard:  Select the “TRM Service Standard” that relates to the identified “SRM Component,” as defined according to the FEA mappings.

Service Specification (i.e., vendor and product name):  Provide information on the specified technical standard or vendor product mapped to the FEA TRM Service Standard, including model or version numbers, as appropriate.

Reuse & Information Sharing

Major IT initiatives must fill out the information listed in the figure below.

Figure 30:  Reuse & Information Sharing

46. Will the application leverage existing components and/or applications across the Government (i.e., FirstGov, Pay.Gov, etc.)? Indicate whether or not the initiative will leverage other existing applications across the government

46a.  If “yes,” please describe.:  If “Yes”, describe the applications (e.g., eGov initiatives, etc..)

47. Does this initiative provide the public with access to a government automated information system?  Indicate whether or not the initiative will provide the public assess to a government automated information system. If “Yes”, respond to sub-question “a”. If “Yes” to sub-question “a”, respond to sub-question “1”.

47a. If “yes,” does customer access require specific software (e.g., a specific web browser version)

47b. If “yes,” provide the specific product name(s) and version number(s) of the required

FEA Primary Business Reference Model Mapping

This section is required in the Exhibit 53 and will cross-populate into eCPIC. Please refer to GSA’s Exhibit 53 Guidance for detailed information on completing this section.

Figure 31: Primary BRM Mapping

FEA Business Reference Model: Major IT initiatives will use this table, as illustrated in Figure 32, to demonstrate how this major IT initiative aligns with the FEA Business Reference Model (BRM). Initiative owners must list the Business Areas, Line of Business, Sub Function, and check whether or not the business area is a primary mapping to the FEA BRM.

Figure 32: FEA BRM BY09

## Part II: Planning, Acquisition and Performance

Major IT initiative owners should only fill out this information for initiatives identified as “Planning” or “Full Acquisition,” or “Mixed Life-Cycle” initiatives in response to Question 6 in Part I, Section A.

### Part II.A:  Alternatives Analysis

An alternatives analysis for major IT initiatives should encompass an assessment of risk and how potential risks can impact the life cycle cost estimate. A viable cost benefit analysis should be completed as part of the alternatives analysis process. OMB requires that three alternatives, in addition to the current baseline, i.e., the status quo, be considered in-depth and documented appropriately.  The cost benefit analysis should include comprehensive estimates of the projected benefits and costs for each viable alternative.  Costs, quantitative benefits, and qualitative benefits (benefits which cannot be valued in dollars) are required.  Qualitative benefits can be evaluated using relative numeric values to enable a comparison between alternatives.  Sunk costs (costs incurred in the past) and realized benefits (savings or efficiencies already achieved) are out-of-scope for a cost benefit analysis since past experience is relevant only in helping estimate future benefits and costs.  Initiatives should be initiated or continued only if the projected benefits exceed the projected costs.  The level of detail and rigor of a cost benefit analysis should be commensurate with the size, complexity, and cost of a project.  Cost/benefit projections should be calculated for all viable alternatives.  Efforts should be made to link performance metrics identified earlier to the alternatives analysis.

To perform well in this section, an initiative must have (1) risk-adjusted life cycle costs and benefits that have been calculated; (2) an Alternatives Analysis date that is within 3 years prior to OMB BY submission on September 10, 2007; (3) an Alternatives Analysis that includes the Status Quo + 3 alternatives; (4) a sound explanation of quantitative benefits (e.g., NPV, ROI, etc.); and (5) a sound explanation of qualitative benefits. Additionally, the quantitative data in this section should be consistent with other sections of the Exhibit 300, e.g., Summary of Spending, Performance Baseline tables, etc.

Please refer to GSA’s Alternatives Analysis Guide in Appendix A for detailed guidance and tools to support Alternatives Analysis development.

Analysis Background:  Major IT initiative owners must fill out the information in Figure 33.

Figure 33:  Analysis Background

48. Did you conduct an alternatives analysis for this initiative?  Please indicate whether or not an alternative analysis was conducted for this initiative.

48a. If “yes,” provide the date the analysis was completed? If “Yes”, provide date of completion. An Alternatives Analysis is considered up-to-date if it was conducted within three years prior to the date of OMB submission (September 10, 2007).

48b. If “no,” what is the anticipated date this analysis will be completed? If “No”, provide anticipated date of completion

48c. If no analysis is planned, please briefly explain why not: If “No”, provide anticipated date of completion or an explanation. OMB expects that an alternative analysis, particularly for E-Gov projects, has been conducted.

Alternatives Table BY09:  Major IT initiative owners must use the results of your alternatives analysis to complete the Alternatives Table in Figure 34. OMB expects the alternatives analysis to be risk adjusted and to account for risk mitigation strategies that should be identified in the initiative’s risk management plan. Identify the process for risk-adjusting the life cycle cost estimates and describe any assumptions used.

Figure 34:  Alternatives Table

Send to OMB: Click this box if you have more than the Status Quo and three alternatives and would like certain alternatives sent to OMB. The XML schema sent to OMB will only allow for the status quo plus three, even though eCPIC accommodates room for more.

Alternative Analyzed:  Provide a title of the alternative

Description of Alternative:  Provide a description of each alternative

Risk Adjusted Lifecycle Costs Estimate  Identify the lifecycle cost estimate of the alternative.

Risk Adjusted Lifecycle Benefits Estimate  Identify the risk adjusted life cycle benefit.

Selected Alternative:  The selected alternative should have a life cycle cost estimate that is close to the figures documented in the Summary of Spending Table. Should this not be the case, document the reason for the discrepancy. Major IT initiative owners must also fill out the following information:

Figure 35: Selected Alternative Table

48. Which alternative was selected by the Agency’s Executive/Initiative Committee and why was it chosen? Identify the selected alternative and describe why it was chosen. Describe any criteria used to compare the alternatives. Provide relevant financial data, e.g. costs, benefits, return on initiative, and use this information to make a case for the selected alternative. OMB does not necessarily expect that the selected alternative is the lowest cost alternative. Should a higher cost alternative be chosen, please explain why and describe the qualitative criteria used, e.g., reduces duplication, automates multiple processes, etc.

49. What specific qualitative benefits will be realized? Identify qualitative benefits of the selected alternatives. Potential answers may include increase user satisfaction, automate processes across the agency, align to business objectives, etc.

Legacy System BY09:  Major IT initiative owners must complete the information in Figure 36 as part of the Alternatives Analysis section of the BY09 OMB Exhibit 300

Figure 36:  Legacy System

50. Will the selected alternative replace a legacy system in-part or in-whole? Answer “Yes” or “No” as applicable to the initiative

50a. If “Yes,” are the migration costs associated with the migration to the selected alternative included in this initiative, the legacy initiative, or in a separate migration initiative? Select the applicable choice from the following selection:  This Initiative, Legacy Initiative, Migration Initiative

50b. If “Yes”, please provide the following information:

System Name: Provide legacy system name

System UPI: Provide legacy system UPI

Date of the System Retirement: Provide the anticipated date that the system will be retired

### Part II.B: Risk Management BY09

Major IT initiatives must complete the information in Figures 37 and 38 regarding risk management. OMB expects that initiatives will have a risk management plan and may ask for appropriate documentation. Initiative owners should have performed a risk assessment during the early planning and initial concept phase of this initiative’s life-cycle, developed a risk-adjusted life-cycle cost estimate and a plan to eliminate, mitigate or manage risk, and be actively managing risk throughout the initiative’s life-cycle.

To perform well in this section, initiatives must (1) calculate risk-adjusted life cycle costs and benefits; (2) have a risk management plan that is current prior to 3 years of OMB BY submission; (3)  have a sound description of how investment risks are reflected in life cycle cost estimate and investment schedule; (4) have valid responses within the security section, including a C&A within 3 years; and (5) have sent a valid and current Risk Management Plan to GSA OCIO.

Figure 37:  Risk Management Plan BY09

RISK MANAGEMENT (All Capital Assets)

51.  Does the initiative have a risk management plan.  Identify whether or not the initiative has a risk management plan.

51a. If “Yes,” what is the date of the risk management plan? Provide the date of the plan. A risk management plan is considered current if it within 3 years prior to the OMB BY submission date (September 10, 2007).

51b. Has the Risk Management Plan been significantly changed since last year’s submission to OMB? Answer “Yes” or “No” as applicable to the project.

51c. If “Yes”, describe any significant changes:  If “Yes”, identify the date of the last update and describe any significant changes that may have occurred since the last budget submission.

52 If there currently is no plan, will a plan be developed? Answer “Yes” or “No” as applicable to the project

52a. If “Yes,” what is the planned completion date? Provide the planned completion date of the risk plan.

52b.If “no,” what is the strategy for managing the risks?   If no risk management plan is in place, identify a date for planned completion or an alternative strategy for managing risk.

Figure 38:  Initiative Risk BY09

Initiative owners must provide a concise narrative on their means to account for risk when performing lifecycle cost projections and developing their performance baseline. The data in Figure 38 is for internal GSA use only as part of the quarterly Control Review, and will not be transmitted to OMB.

### Part II.C: Cost and Schedule Performance BY09

Major IT initiative owners should answer the questions in Figures 39-41 about the status of this initiative. Include information on all appropriate capital assets supporting this initiative except for assets in which the performance information is reported in a separate exhibit 300.

EVM is required only on DME portions of initiatives. For mixed lifecycle initiatives, O&M milestones should still be included in the table (Comparison of Initial Baseline and Current Approved Baseline). This table should accurately reflect the milestones in the initial baseline, as well as milestones in the current baseline.

Figure 39: Earned Value BY09

53. Does the earned value management system meet the criteria in  ANSI/EIA Standard-748? Answer, “Yes” or “No” according to whether the initiative is utilizing EVM and project management best practices that are compliant with the 32 criteria of the ANSI Standard. (For additional information, refer to GSA’s EVM Guide on the GSA Insite EVM webpage (http://insite.gsa.gov/Insite/gsa/ep/channelView.do?pageTypeId=8624&channelId=-9205)

Figure 40:  Cost/Schedule Variance BY09

54. Is the CV% or SV% greater than ± 10%? (CV%= CV/EV x 100; SV%= SV/PV x 100):  Indicate whether or not the cost and schedule variances are outside of the 10% threshold that OMB has identified as an acceptable threshold.

54a. If “Yes,” was it the? CV, SV or Both:  Provide variance data if it is outside the threshold

54b. If “Yes,” explain the variance: Provide an explanation of the variance. (long text)

54c. If “Yes,” describe the corrective actions:  Identify corrective actions as necessary.

Complete the table in Figure 41 to compare actual performance against the current performance baseline and to the initial performance baseline.

###### Figure 41:  Performance Baseline BY09

55. Has the initiative re-baselined during the past fiscal year? Answer “Yes” or No

55a  If “Yes”, when was it approved by the agency head? Identify date of approval.

In the Current Baseline section, for all milestones listed, you should provide both the baseline and actual completion dates (e.g., “03/23/2003”/ “04/28/2004”) and the baseline and actual total costs (in $ Millions).  In the event that a milestone is not found in both initial and current baseline, leave the associated cells blank. Note that the “Description of Milestone” and “Percent Complete” fields are required. Indicate ‘0’ for any milestone no longer active. Note: cost data in the performance baselines must align to the information in the Summary of Spending and Funding Sources table.

Consult Appendix F for GSA-specific guidance on completing the performance baseline reporting table.

## PART III : For “Operation and Maintenance” initiatives ONLY (Steady State)

### III.A: Risk Management Plan BY09

Major IT initiatives must complete the information in Figures 42 regarding risk management. OMB expects that initiatives will have a risk management plan and may ask for appropriate documentation. Initiative owners should have performed a risk assessment during the early planning and initial concept phase of this initiative’s life-cycle, developed a risk-adjusted life-cycle cost estimate and a plan to eliminate, mitigate or manage risk, and be actively managing risk throughout the initiative’s life-cycle.

To perform well in this section, initiatives must (1) calculate risk-adjusted life cycle costs and benefits; (2) have a risk management plan that is current prior to 3 years of OMB BY submission; (3)  have a sound description of how investment risks are reflected in life cycle cost estimate and investment schedule; (4) have valid responses within the security section, including a C&A within 3 years; and (5) have sent a valid and current Risk Management Plan to GSA OCIO.

Figure 42:  Risk Management Plan BY09

56.  Does the initiative have a risk management plan.  Identify whether or not the initiative has a risk management plan.

56a. If “Yes”, what is the date of the risk management plan? Provide the date of the plan. A risk management plan is considered current if it within 3 years prior to the OMB BY submission date (September 10, 2007).

56b. Has the Risk Management Plan been significantly changed since last year’s submission to OMB? Answer “Yes” or No as applicable to the project.

56c. If “Yes”, describe any significant changes:  If “Yes”, identify the date of the last update and describe any significant changes that may have occurred since the last budget submission.

57 If there currently is no plan, will a plan be developed? Answer “Yes” or No as applicable to the project

57a. If ““Yes”,” what is the planned completion date? Provide the planned completion date of the risk plan.

57b. If “no,” what is the strategy for managing the risks?   If no risk management plan is in place, identify a date for planned completion or an alternative strategy for managing risk.

### III.B: Cost Schedule and Performance BY09

OMB will expect GSA to manage its initiatives for performance. The questions in Figures 43 and 44 should be answered to summarize data on how the initiative is performing.

OMB will expect an operational analysis to be conducted on steady state initiatives.  Operational Analysis is a method of examining the current performance of an operational (steady-state) initiative and measuring that performance against an established set of cost, risk and value parameters.  The operational analysis process was developed to periodically evaluate steady-state initiatives and ensure that they are continuing to meet cost, risk and value expectations

Figure 43:  Operational Analysis BY09

58. Was an operational analysis conducted? Answer “Yes” or No, as applicable to the initiative. An operational analysis is considered current if it is within one year prior to OMB submission (September 10, 2007).

58a.  If “Yes”, provide the date the analysis was completed. Identify the date of the operational analysis.

58b.  If “Yes”, what were the results? Describe the results of the operational analysis.

58c.   If “no,” please explain why it was not conducted and if there are any plan to conduct operational analysis in the future.  If no, indicate why not and any future plans to conduct an operational analysis.

Figure 44:  Performance Baseline BY09

59. What costs are included in the reported Cost/Schedule/Performance information (Government Only/Contractor Only/Both)? Identify costs included and classify by government only, contractor only, or both

Complete the table in figure 44 to compare actual cost performance against the planned cost performance baseline.  Milestones reported may include specific individual scheduled preventative and predictable corrective maintenance activities, or may be the total of planned annual operation and maintenance efforts).

Please consult Appendix F for GSA-specific guidance on performance baseline reporting.

## PART IV: Planning For “Multi-Agency Collaboration” ONLY

Part IV should be completed only for initiatives identified as an E-Gov initiative, a Line of Business (LoB) Initiative, or a Multi-Agency Collaboration effort (i.e., Shared Service Provider).  The “Multi-Agency Collaboration” choice should be select in response to Question 6 in Part 1, Section A above. Initiatives identified as “Multi-Agency Collaboration” will complete only Parts I and IV of the Exhibit 300.

Initiatives that should complete this section include the following:

- eAuthentication

- eTravel

- Infrastructure Optimization Initiative

- Federal Asset Sales (eFAS)

- Financial Management Line of Business, Managing Partner

- Integrated Acquisition Environment

- USA Services

- Pegasys/Financial Management Shared Service Provider

- ePayroll-PAR

### Part IV.A:  Multi-Agency Collaboration Oversight (All Capital Assets)

Figure 45:  Stakeholders BY09

As a joint Exhibit 300, please identify all the agency stakeholders (all participating agencies, this should not be limited to agencies with financial commitment).  All agency stakeholders should be listed regardless of approval.  If the partner agency has approved this joint exhibit 300 please provide the date of approval.

Partner Agency:  Insert partner agency name here. All partner agencies for the initiative must be listed and approval must be gained before submission.

Joint Exhibit approval date:  Insert date that the partner agency approved the Exhibit 300.

Figure 46:  Partner Capital Assets BY09

Identify all partner agency capital assets supporting the common solution (section 300.7); Managing Partner capital assets should also be included in this joint Exhibit 300.  These capital assets should be included in the Summary of Spending table of Part I, Section B. All partner agency migration initiatives (section 53.4) should also be included in this table.  Funding contributions/fee-for-service transfers should not be included in this table.  (Partner Agency Asset UPIs should also appear on the Partner Agency’s Exhibit 53.)

Partner Agency:  Insert partner agency name here.

Partner Agency Asset Title:  Provide the title of the Partner Agency Asset that supports the common solution.

Partner Agency Exhibit 53 UPI (BY2009) Provide the Partner Agency Exhibit 53 UPI for that asset.

Figure 47:  Partner Funding BY09

For jointly funded initiative activities, provide the following data in the “Partner Funding Strategies Table,” including: the name(s) of partner agencies; the UPI of the partner agency initiatives; and the partner agency contributions for CY and BY. Please indicate partner contribution amounts (in-kind contributions should also be included in this amount) and fee-for-service amounts. (Partner Agency Asset UPIs should also appear on the Partner Agency’s Exhibit 53.  For non-IT fee-for-service amounts the Partner exhibit 53 UPI can be left blank.)

The remainder of the workflow for Part IV is dependent on whether the major IT initiative is DME/Mixed Lifecycle or in O&M.

### Part IV: Alternatives Analysis (DME/Mixed Lifecycle only)

Refer to the guidance in Part II A for the Alternatives Analysis. Specific guidance on the Quantitative Benefits table is listed below.

Figure 48: Alternatives Analysis

List the specific quantitative benefits will be realized (using current dollars).  Use the results of your alternatives analysis to complete this table.

### Part IV Risk Management (DME/Mixed Lifecycle)

Refer to the guidance in Part II.B.

### Part IV Risk Management (O&M Lifecycle)

Refer to the guidance in Part III.A.

### Part IV Cost and Schedule Performance Information (DME/Mixed Lifecycle)

For DME and mixed lifecycle initiatives, refer to the guidance in Part II.C.

### Part IV: Cost and Schedule Performance Information (O&M Lifecycle)

For O&M initiatives, refer to the guidance in Part III.C .

# APPENDIX A:  QUANTITATIVE APPROACH FOR CONDUCTING ALTERNATIVES ANALYSIS

This document provides guidance for conducting a quantitative alternatives analysis.  An alternatives analysis serves as a means for systematically comparing and evaluating solutions on the basis of cost, benefit, and risk parameters.  This approach is recommended for supporting IT investment decision-making when a project is in a critical phases of its lifecycle.  The analysis includes a future focus, for IT decisions.

OMB recommends this detailed approach when selecting an alternative to meet the needs and requirements of the organization.  Industry best practices recommend that an alternatives analysis be revisited once every three years.  The seven steps that are necessary for conducting this level of analysis are highlighted below.  OMB requires the analysis of the status quo plus three alternatives.  The alternatives analysis should be based on current information, and all alternatives provided should be feasible.

Step 1:  Analyze the Current Environment

The first step in conducting an alternatives analysis is to understand the current operating or "status quo" environment.  This will provide a baseline for making comparisons between the existing and the proposed environment for each of the identified alternatives.  Almost every investment, either in facilities, personnel, technology, or knowledge affects numerous parts of the organization. Understanding how a potential investment impacts the current environment is critical in evaluating the return on investment and the expected short and long term values of the project.

Step 2: Identify Future Environment Requirements

After evaluating the current environment, the results of the current process should be compared to the stated objectives of the future environment.  The outcome of this comparison enables the organization to determine its remaining requirements of the current environment and identify change opportunities.  Once the opportunities for change have been identified, potential solutions must be developed.  These solutions will become the investment alternatives that you should evaluate.  By this point, the organization has analyzed its current environment, determined what needs to be improved, and can identify investment alternatives that will meet its future requirements.

For Mixed Life Cycle investments, the alternatives should be focused on evaluating the DME portion of the overall spending for the investment.

Step 3:  Identify Viable Alternatives

Once potential alternatives have been identified and the decision has been made to explore investing in a project, the alternatives are narrowed to a few viable options.  The list of alternatives will include the status quo, as well as three other potential investments for comparing and selecting the appropriate alternative.  To develop a short-list of alternatives, each alternative is evaluated using non-financial, qualitative factors.  Asking whether the organization can absorb the change and gauging the probable long-term success of the investment is critical before starting to calculate costs and benefits.

Examples of Alternatives include:

- Status Quo

Status Quo, or an explanation of the current method of meeting the mission need,  should always be one of the alternatives. You should explain the limitations and/or adverse effects on performance associated with the current status. Presumably, you want to make an investment because the current way of meeting the mission need is inadequate. This explains why.

- Outsourcing
If you choose outsourcing as an alternative, you will be analyzing and documenting the benefits, risks and costs of outsourcing the function.

- Government Owned and Operated
If you choose this as an alternative, you will be analyzing and documenting the benefits, risks and costs of maintaining the function within and ownership of assets by the Government.

- Process/Organizational Changes Only
This alternative could include a reorganization in the agency or division or the reengineering of a particular business process that helps you meet a mission need. You will be analyzing and documenting the benefits, risks and costs of restructuring processes or functions within the agency vs. meeting the mission need with the investment.

- Information Technology/System Only
Investing in a system or IT asset without any underlying organizational changes.

An alternative could also be stated as a mixture of the options listed above.

Step 4:  Conduct Cost Analysis for the Status Quo and Each Alternative

The first step in conducting a cost estimate is to develop a cost element structure (CES) that categorizes the major cost components for the status quo and each alternative.  This includes all costs that will be incurred in the development, production, and operations and maintenance phases of the projects.  By first developing a cost estimate for the status quo, you can determine the resources required to operate and maintain the existing environment and determine the additional resources that will be required to develop, deploy, and maintain the proposed alternatives.

Step 5:  Conduct Benefit Analysis for Each Alternative

A business case identifies both the quantitative and qualitative benefits of an alternative when evaluating total benefits.  Quantitative benefits include the dollar saving investments to both the federal government and key stakeholders that may be obtained by implementing the proposed initiative.  However, many benefits for certain public government investments are qualitative in nature and do not lead directly to dollar savings.  Improvements in customer service and employee morale are certainly recognized as benefits, but rarely can be included in the dollar-valued benefits stream or return on investment measures. Because many public goods are difficult to reliably quantify in dollar units, non-monetary benefits are also vital to understand the total implementation outcome of the investment.

The following quantitative and qualitative benefits should be addressed when evaluating total annual benefits for each alternative:

- Qualitative Benefits

- Cost Savings

- Cost Avoidance

- Stakeholder Benefits

- Non-Monetary Quantitative Benefits

Each of these benefit categories is described in further detail in the following sections.  Examples for calculating each of these benefits are also provided.

Qualitative Benefits – This includes intangible benefits that are not dollar-quantifiable (e.g., employee morale, customer satisfaction).

Cost Savings – This includes the savings that will result in a direct budget reduction for operations and maintenance costs between the status quo and proposed alternative environments (e.g., reduction in software/hardware maintenance costs).  For example, if under the status quo system, GSA must currently pay $1 million for annual hardware maintenance costs and will only pay $850,000 under the proposed alternative, then GSA will save $150,000 annually.  This should be noted as a cost savings in your analysis.  Similarly, if the proposed alternative will reduce the need for annual outsourcing by a certain amount, then this should be noted as well.  The total operations and maintenance savings between the alternatives should be identified.

Cost Avoidance – This includes the costs that will not be incurred under the proposed alternative that would otherwise have been incurred if the investment had not been made (e.g., avoid having to hire additional staff that would have been required under the status quo).  For example, if under the alternative, GSA will not have to hire the additional 5 employees that would have been required to support increased workload under the status quo.  The cost associated with the 5 employees should be calculated and included in the benefits analysis.  The following section provides an example for conducting this cost avoidance analysis.

Question:  How many additional FTEs will not need to be hired if the proposed alternative is selected?

Answer:  5 FTEs

Question:  When would the FTEs have been hired?

Answer:  Year 2 and each year thereafter

Question:  What is the GS level of the 5 FTEs

Answer:  GS-13

Calculation:  To determine the cost avoidance associated with these employees, you must first take the annual salary of a GS-13 employee (per GSA Guidance, a GS-13 salary is $79,397 per annum)) and multiply this salary by a projected fringe benefits (32.8%) to determine the fully-burdened cost of labor.  This rate includes the cost of the following items:  personnel benefits (Social Security, Federal Employees Group Life Insurance, Federal Employees Health Benefit, Federal Employees Retirement System, Civil Service Retirement System, and Thrift Savings Plan); overtime, cash awards, pay differentials, travel, ADP equipment, non-ADP equipment, repairs and alterations to office space, etc.

The following equation can be used to determine the cost avoidance:

Cost Avoidance = # of FTEs avoided x Salary of Employee x Fringe Benefits

=   5 FTEs        x          $79,397          x       1.328

= $ 527,196.08

Stakeholder Benefits – This includes the savings that would be incurred by key stakeholders outside of the organization (e.g., benefits to public citizens or private industry).  For example, if an e-government initiative was implemented at GSA that would allow private citizens to submit information on-line instead of having to mail it directly to the agency, then you could determine the postage savings that would be achieved by the citizens.  By answering the following questions, you could estimate the potential stakeholder benefits:

Question:  How many citizens send this information to GSA annually?

Answer:  200,000 citizens

Question: How many pieces of paper are sent on average?

Answer:  3 pages

Question:  What is the postage cost associated with this mailing?

Answer:  $.37/mailing

Calculation:  The stakeholder savings could be calculated with the following equation:

Stakeholder Savings = # of Citizens Mailing Information x Average Cost of Mailing

=   200,000       x         $.37

= $ 74,000

Non-Monetary Quantitative Benefits – This includes the performance improvements that will be achieved as a result of implementing the initiative (e.g., decreased response time for customer service calls).  For example, suppose one alternative will decrease the amount of time that will be required to address level one customer service calls at GSA's help desk support center.  You can illustrate improved performance levels by filling-in the following table:

| Performance Measure | Current Target | Future Target | Business Process Improvement |
| --- | --- | --- | --- |
| Average Customer Service Call | 8 minutes | 5.5 minutes | Improve customer service by reducing the amount of time to process a service call |
| Number of Service Regions Covered by Help Desk Support | 5 regions | 10 regions | Increase help desk coverage to GSA employees |

Similar to preparing a cost estimate, the benefit analysis should include potential benefits over the same ten-year period.

Step 6:  Evaluate Economic Measures Among the Alternatives

After calculating the costs and benefits for each alternative, comparisons can be made between the status quo and viable alternatives. In order to compare costs and benefits between alternatives, it is necessary to discount future costs and benefits to reflect the time value of money. The time value of money reflects the fact that money in hand today is more valuable than an identical amount of money received in the future.  The following section provides an overview of what is discounting and how it should be applied when conducting cost/benefit analysis of alternatives.

What is discounting?

Question:  Why is current money more valuable than future money?

Answer:  Because you can do something with it now, e.g., the ability to buy food today is clearly more valuable than the ability to buy food a year from now.

Therefore, benefits and costs are worth more if they are experienced sooner.  We discount cost streams when we need to compare incurring costs at different times.  For example, if cost is the only deciding factor, which investment should the organization invest in if the total cost is $500,000 over a five year period?

| CONSTANT $ | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Project A |  |  |  |  |  |  |
|  | PV Cost | $100,000 | $100,000 | $100,000 | $100,000 | $100,000 | $500,000 |
| Project B |  |  |  |  |  |  |
|  | PV Cost |  |  |  |  | $500,000 | $500,000 |
| Project C |  |  |  |  |  |  |
|  | PV Cost | $500,000 |  |  |  |  | $500,000 |
| Project D |  |  |  |  |  |  |
|  | PV Cost |  | $500,000 |  |  |  | $500,000 |

At first glance it may appear that the total investment is the same, since they each total $500,000.  However, since the costs are incurred over different years, there are actual different cost implications for the organization.

The organization should invest in the project with the lowest discounted cost stream (given that the benefits for the alternatives are the same).  In the example below, Project B has the lowest cost in terms of present value.  For example, you need $500,000 today for Project C.  Alternatively, you could put $422,900 in a bank today and receive the $500,000 you need in year 5 for Project B.  Economists contend that you are better off with Project B because you can do something else with the $59,190 you did not put in the bank.

| DISCOUNTED $ | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Program Year | 0 | 1 | 2 | 3 | 4 |  |
| Discount Factor | 1.0000 | 0.9764 | 0.9308 | 0.8873 | 0.8458 |  |
| Project A |  |  |  |  |  |  |
|  | PV Cost | $100,000 | $97,640 | $93,080 | $88,730 | $84,580 | $464,030 |
| Project B |  |  |  |  |  |  |
|  | PV Cost |  |  |  |  | $422,920 | $422,920 |
| Project C |  |  |  |  |  |  |
|  | PV Cost | $500,000 |  |  |  |  | $500,000 |
| Project D |  |  |  |  |  |  |
|  | PV Cost |  | $488,180 |  |  |  | $488,180 |

OMB Circular A-94 Appendix C provides the appropriate discount rates for conducting the alternative analysis.  Based on the ten-year real interest rates on Treasury notes and bonds, the current discount rate is 4.9%.  The discount factor is equal to 1/(1+i)t where i is the interest rate and t is the number of years from the date of initiation for the project.

How do you discount costs?

To illustrate this concept, a five-year estimate for three projects is provided in the following tables.  By following each of the three steps, you will be able to discount both the costs and benefits for your project.

Step 1 – Determine the cost of each alternative in constant dollars

| CONSTANT $ | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Project A (Status Quo) |  |  |  |  |  |  |
|  | Investment |  |  |  |  |  |  |
|  | O&M | $1,000,000 | $1,000,000 | $1,000,000 | $1,000,000 | $1,000,000 | $5,000,000 |
|  | Total Cost | $1,000,000 | $1,000,000 | $1,000,000 | $1,000,000 | $1,000,000 | $5,000,000 |
| Project B (Alternative 1) |  |  |  |  |  |  |
|  | Investment | $500,000 |  |  |  |  | $500,000 |
|  | O&M | $1,000,000 | $850,000 | $850,000 | $850,000 | $850,000 | $4,400,000 |
|  | Total Cost | $1,500,000 | $850,000 | $850,000 | $850,000 | $850,000 | $4,900,000 |
| Project C (Alternative 2) |  |  |  |  |  |  |
|  | Investment | $200,000 |  | $100,000 |  | $200,000 | $500,000 |
|  | O&M | $1,000,000 | $1,100,000 | $1,100,000 | $1,100,000 | $1,100,000 | $,400,000 |
|  | Total Cost | $1,200,000 | $1,100,000 | $1,200,000 | $1,100,000 | $1,300,000 | $5,900,000 |
| Project D (Alternative 3) |  |  |  |  |  |  |
| Investment | $200,000 | $100,000 | $200,000 |  |  | $500,000 |
| O&M | $1,000,000 | $1,100,000 | $1,100,000 | $1,100,000 | $1,100,000 | $400,000 |
| Total Cost | $1,200,000 | $1,100,000 | $1,200,000 | $1,100,000 | $1,300,000 | $5,900,000 |

Step 2 – Determine the benefits of each alternative in constant dollars

(The assumptions for calculating cost savings, cost avoidance, and stakeholder benefits for Alternatives 1, 2, and 3 are provided in the previous section entitled Step 5:  Conduct Benefit Analysis for Each Alternative.)

| CONSTANT $ | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  | Project A (Status Quo) Cost Savings |  |  |  |  |  |  |
|  | Cost Avoidance |  |  |  |  |  |  |
|  | Stakeholder Benefits |  |  |  |  |  |  |
|  | Total Benefits |  |  |  |  |  |  |
|  | Project B (Alternative 1) Cost Savings | $ - | $150,000 | $150,000 | $150,000 | $150,000 | $600,000 |
|  | Cost Avoidance |  | $573,136 | $573,136 | $573,136 | $573,136 | $2,292,544 |
|  | Stakeholder Benefits |  | $68,000 | $68,000 | $68,000 | $68,000 | $272,000 |
|  | Total Benefits |  | $791,136 | $791,136 | $791,136 | $791,136 | $3,164,544 |
|  | Project C (Alternative 2) Cost Savings |  | $(100,000) | $(100,000) | $(100,000) | $(100,000) | $(400,000) |
|  | Cost Avoidance |  | $571,696 | $571,696 | $571,696 | $571,696 | $2,286,784 |
|  | Stakeholder Benefits |  | $68,000 | $68,000 | $68,000 | $68,000 | $272,000 |
|  | Total Benefits |  | $539,696 | $539,696 | $539,696 | $539,696 | $2,158,784 |
|  | Project D (Alternative 3) Cost Savings |  | $100,000 | $100,000 | $100,000 | $100,000 | $400,000 |
|  | Cost Avoidance |  | $571,696 | $571,696 | $571,696 | $571,696 | $2,286,784 |
|  | Stakeholder Benefits |  | $68,000 | $68,000 | $68,000 | $68,000 | $272,000 |
|  | Total Benefits |  | $539,696 | $539,696 | $539,696 | $539,696 | $2,957,784 |

The costs and benefits are then discounted by the appropriate discount factor (4.9%) to account for the time value of money. Each of the tables provides only a five-year estimate for illustrative purposes.  The actual estimate should cover a ten-year period.

Step 3 – Discount the costs and benefits

| DISCOUNTED $ | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Program Year | 0 | 1 | 2 | 3 | 4 |  |
| Discount Factor | 1.0000 | 0.9764 | 0.9308 | 0.8873 | 0.8458 |  |
| Project A (Status Quo) |  |  |  |  |  |  |
|  | PV Investment |  |  |  |  |  |  |
|  | PV O&M | $1,000,000 | $976,400 | $930,800 | $887,300 | $845,800 | $ 4,640,300 |
|  | PV Total Cost | 1,000,000 | 976,400 | 930,800 | 887,300 | 845,800 | $ 4,640,300 |
|  | PV Cost Savings |  |  |  |  |  |  |
|  | PV Cost Avoidance |  |  |  |  |  |  |
|  | PV Stakeholder Benefits |  |  |  |  |  |  |
|  | PV Total Benefits |  |  |  |  |  |  |
| Project B (Alternative 1) |  |  |  |  |  |  |
|  | PV Investment | $500,000 |  |  |  |  | $500,000 |
|  | PV O&M | $1,000,000 | $829,940 | $791,180 | $754,250 | $718,930 | $4,094,300 |
|  | PV Total Cost | $1,500,000 | $829,940 | $791,180 | $754,250 | $718,930 | $4,594,300 |
|  | PV Cost Savings |  | $146,460 | $139,620 | $128,659 | $126,870 | $541,609 |
|  | PV Cost Avoidance |  | $559,610 | $533,475 | $508,544 | $484,758 | $2,086,387 |
|  | PV Stakeholder Benefits |  | $66,395 | $63,294 | $60,336 | $57,514 | $247,539 |
|  | PV Total Benefits |  | $772,465 | $736,389 | $697,539 | $669,143 | $2,875,535 |
| Project C (Alternative 2) |  |  |  |  |  |  |
|  | PV Investment | $200,000 |  | $93,080 |  | $169,160 | $ 462,240 |
|  | PV O&M | $1,000,000 | $1,074,040 | $1,023,880 | $976,030 | $930,380 | $5,004,330 |
|  | PV Total Cost | $1,200,000 | $1,074,040 | $1,116,960 | $976,030 | $1,099,540 | $5,466,570 |
|  | PV Cost Savings |  | $(97,640) | $(93,080) | $(88,730) | $(84,580) | $(364,030) |
|  | PV Cost Avoidance |  | $558,204 | $532,135 | $507,266 | $483,540 | $2,081,145 |
|  | PV Stakeholder Benefits |  | $66,395 | $63,294 | $60,336 | $57,514 | $247,539 |
|  | PV Total Benefits |  | $526,959 | $502,349 | $478,872 | $456,474 | $1,964,654 |
| Project D (Alternative 3) |  |  |  |  |  |  |
|  | PV Investment | $200,000 | $97,640 | $186,160 |  |  | $483,800 |
|  | PV O&M | $1,000,000 | $1,074,040 | $1,023,880 | $976,030 | $930,380 | $5,004,330 |
|  | PV Total Cost | $1,200,000 | $1,171,680 | $1,210,040 | $976,030 | $930,380 | $5,488,130 |
|  | PV Cost Savings |  | $97,640 | $93,080 | $88,730 | $84,580 | $364,030 |
|  | PV Cost Avoidance |  | $558,204 | $532,135 | $507,266 | $483,540 | $2,081,145 |
|  | PV Stakeholder Benefits |  | $66,395 | $63,294 | $60,336 | $57,514 | $247,539 |
|  | PV Total Benefits |  | $722,239 | $688,509 | $656,332 | $625,634 | $2,692,714 |

After the costs and benefits are discounted, the following three economic measures should be used to compare the economic feasibility of each of the alternative investments:

1.  Net Present Value (NPV) – OMB Circular A-94 states that the standard criterion for deciding whether a government program can be justified on economic principles is net present value – the discounted monetized value of expected net benefits (i.e., benefits minus costs).  Net present value is computed by assigning monetary values to benefits and costs, discounting future benefits and costs using an appropriate discount rate, and subtracting the sum total of discounted costs from the sum total of discounted benefits.  Discounting benefits and costs transforms gains and losses occurring in different time periods to a common unit of measurement.  Programs with positive net present value increase social resources and are generally preferred.  Programs with negative net present value should generally be avoided.  Net Present Value can be calculated by the following equation:

NPV  = Present Value (PV) (Annual Benefits) – Present Value (PV) (Annual Costs)

= [(PV O&M Savings Between Status Quo and Alternative + PV Cost Avoidance +

PV Stakeholder Benefits) – PV Investment Costs]

To illustrate this measure with the previous example, the NPV has been calculated for Alternative 1.  The same process should be used to compute the other alternatives' NPVs.

Alternative 1 NPV =  ($541,609 + $2,086,387 + $247,539) - $500,000

= $2,375,535

2.  Return on Investment (ROI) – ROI measures the amount of savings generated for each dollar of investment for an alternative.  In a desirable economic situation, the ROI is greater than one.  If the ROI is equal to one, then there is no advantage in implementing the proposed environment.  The higher the ROI, the greater the economic advantage to the organization.  ROI is calculated by the following equation:

ROI = Present Value Savings/Present Value Investment

= (PV O&M Savings Between Status Quo and Alternative + PV Cost Avoidance +

PV Stakeholder Benefits)/PV Investment Costs)

| Present Value Savings | The present value of any systems operations savings that may arise from the replacement of the status quo by the proposed alternative plus the present value of potential cost avoidance and stakeholder benefits. |
| --- | --- |
| Present Value Investment | The present value of the initial investment for the proposed alternative (development cost plus implementation cost). |

To illustrate this measure, the ROI has been calculated for Alternative 1.  The same process should be used to compute the other alternatives' ROIs.

Alternative 1 ROI  =  ($541,609 + $2,086,387 + $247,539)/ $500,000

= 5.75%

Step 6:  Compare and Recommend an Alternative

Once all of the costs and benefits of the alternatives are understood, a comparison of alternatives may be conducted.  Comparisons must be made in two areas: the financial impact and the strategic value impact per dollar invested.  ROI and NPV metrics represent the return realized by an organization in financial terms.  These metrics allows an organization to understand how they will save money or avoid certain costs through implementation of a particular initiative.

Summary Analysis

|  | Status Quo | Alternative 1 – Enhancement to Status Quo | Alternative 2 – New Systems | Alternative 3 – New Systems |
| --- | --- | --- | --- | --- |
| Discounted Cost | $4.6M | $4.6M | $5.5M | $5.5M |
| NPV | -$4.6M | $2.4M | $1.5M | $2.2M |
| ROI | N/A | 5.75% | 4.25% | 5.57% |

Based on the key measures, Alternative 1 should be selected due to its higher NPV and ROI values and performance score.  However, when comparing and recommending an alternative, it is imperative to also demonstrate that this alternative also best supports the mission of the organization

# APPENDIX B:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY SUBJECT AREA

# APPENDIX C:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY INITIATIVE

# APPENDIX D:  BY09 BUDGET SUBMISSION POINTS OF CONTACT BY BUDGET AREA

###### APPENDIX E:   GSA FUNDING SOURCE & MAX ACCOUNT LIST

APPENDIX F:   Budget Year 2009 (BY09) Guide to OMB 300 Performance Baseline and Earned Value Management (EVM) Reporting

Purpose

This guidance, which is targeted to program managers, project managers, and staff creating Exhibit 300s, is applicable to development / modernization / enhancement (DME), mixed lifecycle and steady state (SS) initiatives. It also impacts Major IT initiatives’ earned value management (EVM) reporting in GSA’s control report activities.

Background

DME efforts fund planning activities, new investment acquisitions, or significant modifications to existing investments that improve capability or performance. Planning activities may include government / contractor personnel costs or other direct costs to identify alternatives for problem solving, develop initial plans, or conduct studies. Acquisition efforts fund specific products and services that are being acquired for an initiative. This may include contractor services, hardware, software, or telecommunications. OMB Circular A-11, Section 300 requires EVM reporting on all DME activities.

SS efforts fund operations & maintenance costs for current capabilities and performance levels. This includes preventative and predictable corrective maintenance activities, such as:

- corrective software maintenance,

- voice and data communications maintenance,

- replacement of broken IT equipment,

- technology refreshments, minor upgrades, and

- government /contractor personnel that work on these activities.

Activities that substantially increase an SS initiative’s capability, performance, and capacity, especially when needed by a certain time, may qualify as DME efforts.

Instructions

In the OMB Exhibit 300, the information for DME and mixed lifecycle initiatives impacts reporting in Part II, Section C, Question 9: Comparison of Initial Baseline and Current Approved Baseline. For SS initiatives, Major IT initiative owners report this information in Part III: Section B, Question 2.b: Comparison of Planned vs. Actual Performance. The applicable information for DME/mixed lifecycle and SS E-Gov initiatives is in Part IV, Section C of the Exhibit 300 E-Gov BY09 template.

All Major IT initiatives must report DME and SS milestones from FY05 and prior through FY09 for their performance baselines using a work breakdown structure (WBS) approach with associated cost estimates to create the set of cost and schedule milestones used to manage and track project performance. GSA OCIO recommends that Major IT initiatives with insight into their performance baselines beyond FY09 report the forecasted full lifecycle of their initiatives.

For each fiscal year detailed, Major IT initiatives’ performance baselines should align to their Summary of Spending tables in Part I, Section B. If they do not align, Project Managers should have an explanation for OMB to support this deviation.

It is inevitable that some milestones will cross fiscal year boundaries. In this case, Major IT initiative owners must track milestones through completion of the activity. Therefore, if a milestone is scheduled to end in FY07, but is delayed, Project Managers must continue to track and report the milestone into FY08. For greater granularity of reporting, Major IT initiative owners may also choose to de-compose milestones into an appropriate number of sub-milestone / phases to stay within the boundary of a single fiscal year, and track the remainder of the activity until completion. Note:  schedule slippages are not sufficient basis for re-baselining.  A project carrying over milestones must justify a change to the planned completion date as part of the control reporting/baseline change request (BCR) process.

Major IT initiative owners cannot alter performance baseline information in the BY09 Exhibit 300 table except in the following situations:

- The Major IT initiative owner submitted a BCR in FY07 that the Information Technology Council (ITC) approved. These initiatives must report that they have re-baselined, along with the date that the ITC approved the BCR.

- The Major IT initiative owner did not properly construct its performance baseline in accordance with GSA guidance. NOTE: In this case, the Major IT initiative owner cannot change planned completion dates or milestone costs. The Major IT initiative owner is only authorized to add the required granularity of detail to meet GSA requirements for performance baseline reporting.

Major IT initiative owners should work with their OCIO liaisons if they have any questions with constructing their performance baselines. Note: the GSA OCIO is performing more comprehensive reviews and scoring of the performance baselines for the BY09 Exhibit 300s. Refer to Appendix G for the specific evaluation criteria of the Performance Baseline reporting.

I. DME/Mixed Lifecycle Initiatives

A. OMB 300 Reporting

PMs should structure their milestones, using an alpha-numeric scheme. Major milestones should follow a three-digit numbering scheme (e.g., 001, 002, etc). Denote sub-milestones by adding letters to the major milestones (e.g., 001A, 001B, etc.).

In the Comparison of Initial Baseline and Current Approved Baseline table, report the following in Electronic Capital Planning and Investment Control (eCPIC):

- Milestone number (use the alpha-numeric scheme noted above)

- Milestone description

- Percent complete

Initial Baseline milestones

- Planned Completion Date

- Total Cost ($M) estimated

Current Baseline milestones

- Completion Date (both planned AND actual)

- Total Cost (both planned AND actual in $M)

- Current baseline variance (both schedule and cost)

Milestone number, milestone description, and percent complete are required fields. In the event that a milestone is not found in both the initial and current baseline, leave the associated cells blank.

B. How to structure the WBS

1. Initial Baseline

GSA’s BY08 Budget Submission Guidance required project managers to create “Initial Baselines” using data from their FY07 OMB 300 I.H.2 table. Major IT initiative owners should not change their “Initial Baseline” tables, unless they are not currently representative of the first performance baselines that were submitted to OMB.

2. Current Baseline

The GSA BY08 Budget Submission Guidance required Project Managers to construct “Current Baselines” using a variety of data sources: FY07 OMB 300 I.H.4, FY07 Summary of Spending, FY06 monthly control reports, and current project management cost and schedule estimates. As a reminder, Major IT initiative owners should not change their current baselines unless they received an approved BCR in FY07 or they did not properly construct their baselines in the BY08 Budget Submission.

Follow this set of instructions to ensure that GSA has a consistent and comprehensive approach to performance baseline reporting. Note the specific instructions on reporting the following:

- FY05 and prior milestones

- FY06 milestones

- FY07 milestones

- FY08 milestones

- FY09 and beyond milestones

The screenshot below illustrates a sample WBS in the eCPIC Cost and Schedule Performance Table for a mixed lifecycle initiative.

Graphic 1: Mixed Lifecycle Performance Baseline Screenshot

a. FY05 and prior Milestones:

Ensure that there is one line item for DME funding and one line item for SS funding, as applicable for the project. The data reported for FY05 and prior must equal the PY2005 Total All Stages PLUS Government FTE costs for this same period, as reported in the FY07 Summary of Spending table. IT Initiative owners with detailed milestones from FY05 and prior can report those milestones in place of the two high-level DME and SS (as applicable) line items.

b. FY06 Milestones:

Initiative owners must ensure that each FY06 control report milestone is represented in the eCPIC performance baseline. Milestones that began in FY06 which will extend into FY07 should continue to be reported until completion.

c. FY07 Milestones:

Initiative owners must ensure that each FY07 control report milestone is represented eCPIC performance baseline. Milestones that began in FY07 which will extend into FY08 should continue to be traced until completion.

d. FY08 Milestones

Develop FY08 milestones in accordance with the GSA systems development lifecycle (SDLC). Although not preferred, you may employ other approved SDLC methodologies, e.g., Rational Unified Process (RUP). GSA Order CIO P 2140.2 life cycle phases are referenced below:

- System Concept Development (DME);

- Planning (DME);

- Requirements Analysis (DME);

- Design (DME);

- Development (DME);

- Integration & Test (DME);

- Implementation (DME);

- Operations & Maintenance (SS); and

- Disposal (SS).

Below is an example milestone set for a Mixed Life Cycle (MLC) initiative:

- 001 DME FY08 Project 1

- 001.A Planning

- 001.B Requirements Analysis

- 002 DME FY08 Project 2

- 002.A Planning

- 002.B Development

- 003 SS FY08 Component

- 003.A Operate System

- 003.B Maintain Data & Software

A project is a temporary endeavor to create a unique service, product or result, A component, also called sub-project or useful segment, is the grouping of severable functionality or services within each initiative.

e. FY09 Milestones and beyond

Include line items for the DME and SS activities that are anticipated in FY09. There must be two Level 1 milestones denoting DME and SS activities, with the applicable projects or components, decomposed into Level 2 sub-milestones beneath them.

GSA OCIO recommends that Major IT initiatives with insight into their performance baselines beyond FY09 report the forecasted full lifecycle of their initiatives.

II. SS Initiatives

A. OMB 300 Reporting

PMs should structure their milestones, using an alpha-numeric scheme. Major milestones should follow a three-digit numbering scheme (e.g., 001, 002, etc). Denote sub-milestones by adding letters to the major milestones (e.g., 001A, 001B, etc.).  In the Comparison of Plan vs. Actual Performance table, report the following in the Exhibit 300 O&M BY09 view of eCPIC

- Milestone Description

- Planned Completion Date

- Planned Total Cost

- Actual Completion Date

- Actual Total Cost

- Cost and Schedule Variance

The eCPIC screenshot below illustrates a sample WBS in the eCPIC Cost and Schedule Performance Table for a SS initiative.

Graphic 2:  Cost, Schedule and Performance Table for SS initiative.

B. How to Structure the WBS

1. Instructions for FY05 and prior – FY09 and beyond Milestones

Follow this set of instructions to ensure that GSA has a consistent and comprehensive approach to performance baseline reporting. Note the specific instructions on reporting the following:

- FY05 and prior milestones

- FY06 milestones

- FY07 milestones

- FY08 milestones

- FY09 and beyond milestones

a. FY05 and prior Milestones:

Ensure that there is one line for SS funding. The data reported for FY05 and prior must equal the PY2005 Total All Stages PLUS Government FTE costs for this same period, as reported in the FY07 Summary of Spending table. Initiative owners with detailed milestones from FY05 and prior can report those milestones in place of the two high-level DME and SS (as applicable) line items.

b. FY06 Milestones:

SS initiatives must ensure that each quarterly FY06 control report milestone is represented in eCPIC Part III, Section B.

c. FY07 Milestones:

SS initiatives must ensure that each quarterly FY07 control report milestone is represented in the eCPIC Part III, Section B.

d. FY08 Milestones

Develop FY08 milestones in accordance with the GSA systems development lifecycle (SDLC). Although not preferred, you may employ other approved SDLC methodologies e.g., Rational Unified Process (RUP). Below is an example milestone set for a SS investment:

- 001 SS FY08 Component 1

- 001.A Operate System

- 001.B Maintain Data & Software

- 002 SS FY08 Component 2

- 002.A Operate System

- 002.B Dispose System

A component, also called a useful segment, is the grouping of severable functionality or services within each initiative.

e. FY09 and Beyond Milestones:

Include line items for the SS activities that are anticipated in FY09. At a minimum, there must be one Level 1 milestone denoting SS activities, with the applicable components decomposed into Level 2 sub-milestones beneath it.

GSA OCIO recommends that Major IT initiatives with insight into their performance baselines beyond FY09 report the forecasted full lifecycle of their initiatives.

Conclusion:

As OMB publishes additional requirements for performance baseline reporting, OCIO will amend this guidance. If IT initiative staff have any questions on how to construct or report on their performance baselines, please contact your OCIO liaison. Liaisons are listed by Major IT initiative in Appendix C

APPENDIX G:   BY09 Exhibit 300 Evaluation Framework

Section 1: Background

The General Services Administration (GSA) Office of the Chief Information Officer (OCIO) has developed the  Exhibit 300 Evaluation Guide to assist in the development of Exhibit 300s (E300s) for submission to the Office of Management and Budget (OMB).\  The intent of this framework is to document and enable Program and Project Managers (PMs) and staff to understand needed information in improving their Exhibit 300 submissions for major IT initiatives.  This process will help achieve the goal of increasing the transparency of IT initiatives, enabling improved decision making by GSA leadership at the enterprise-level, and decreasing the number of initiatives placed on the OMB Management Watchlist. As the mechanism through which OMB staff views each agency’s major or mission-critical IT efforts, the Exhibit 300 is not a substitute for a robust business case or formal project management documentation, but it reflects whether or not those disciplines have been employed in planning and managing the effort.

The evaluation elements included in this guidance correspond to the ten categories utilized by OMB during the BY08 budget submission cycle.  The ten categories include: Project Management, President’s Management Agenda, Acquisition/Contract Strategy, Performance Goals, Security, Privacy, Enterprise Architecture, Cost and Schedule Performance, Alternatives Analysis, and Risk Management.

The GSA OCIO will use these elements to evaluate the Exhibits 300 on a bi-weekly basis, as needed, prior to OMB Submission in September. OCIO CPIC staff will provide the evaluation elements to supporting offices, including the Chief Financial Officer (CFO), IT Security, Office of the Chief Human Capital Officer (OCHCO) Privacy office, OCIO Enterprise Architecture office, and the Office of the Chief Acquisition Officer (OCAO) to provide an independent evaluation of the relevant sections. Supplemental information on suggested content for the 300s is published in the GSA BY09 Exhibit 300 Guidance.

Section 2:  Review Process

All Exhibit 300s will be evaluated by OCIO Capital Planning Staff, in conjunction with subject matter experts (SMEs) from the Office of the Chief Financial Officer (OCFO) budget, OCIO Enterprise Architecture, IT Security, Office of the Chief Acquisition Officer (OCAO), and Office of the Chief Human Capital Officer (OCHCO) Privacy offices. Figure 1 is a map of the roles and responsibilities for the Exhibit 300 Evaluation process.

Figure 1: Exhibit 300 Review Process

Section 3:  Schedule

Exhibit 300s are due to OCIO for internal evaluation no later than July 30th, 2007. Feedback will be distributed on a bi-weekly basis regarding the initiative Exhibit 300 evaluation status from July 30th – September 4th.  Final Exhibit 300s will be submitted to OMB on Monday, September 10th.

OCIO will support PMs and business owners by offering multiple training sessions and other informational sessions.

| Training Type | Day (Tentative) |
| --- | --- |
| Kickoff Meetings |  |
| eGov Kickoff | Wednesday, June 20th |
| General Kickoff | Wednesday, June 27th |
| Comprehensive 300 CPIC Training Session |  |
| SSO Capital Planning Staff—Non-Major Data Requirements | Wednesday, July 11th |
| Major Initiatives – Exhibit 300 Training and Scoring Review | Wednesday, July 11th |
| Potential Targeted “Brown Bag” Topics (3 of 6 options) |  |
| Alternatives Analysis | Wednesday, July 18th; Wednesday, July 25th; Wednesday, August 1st. |
| Performance Baseline Tables/WBS/EVM |  |
| Security/Privacy |  |
| Telling a Consistent Story: Aligning Financial Tables, Contract Table, EVM Table, etc. |  |
| Enterprise Architecture |  |
| Creating a Risk Management Plan |  |
| Bi-weekly Reports |  |
| Updates on 300 Evaluation | Beginning Monday, August 6th and continuing on a bi-weekly basis until September 10th (OMB Submission) |
| GSA OCIO Guidance |  |
| BY09 Exhibit 300 & Exhibit 53 Guidance | Wednesday, July 11th |

Section 4:  Overall Evaluation

Below are the overall evaluation criteria that OCIO, in conjunction with staff from EA, Security, OCAO, and Privacy, will use to review each major IT initiative. A “passing” evaluation consists of an overall score of 31, with specific minimum thresholds required for security and financial data/lifecycle alignment. Please note that the GSA Evaluation Framework is based on the OMB evaluation framework used in prior years, which is subject to change at their discretion.

| Score | Description | Financial Summary & Lifecycle Alignment | Security |
| --- | --- | --- | --- |
| 44-50 | Superior: Strongly documented Exhibit 300. | (1) The Summary of Spending/Full-Time Equivalent Tables match/balance with the Funding Sources Table Costs in these tables are consistent with the Performance Baseline Tables, Contracts Table, & Preferred Alternative. (2) The Financial tables show full lifecycle of the program. | Security sections have a minimum score of 4. |
| 36-43 | Good: Well-documented Exhibit 300. | (1) The Summary of Spending/Full-Time Equivalent Tables match/balance with the Funding Sources Table Costs in these tables are consistent with the Performance Baseline Tables, Contracts Table, & Preferred Alternative. (2) The Financial tables show full lifecycle of the program. | Security sections have a minimum score of 4. |
| 31-35 | Marginally Passing: Very few weak points exist within the Exhibit 300, but it still needs strengthening. Initiative is at risk of placement on the OMB Management Watch List. | (1) The Summary of Spending/Full-Time Equivalent Tables match/balance with the Funding Sources Table Costs in these tables are consistent with the Performance Baseline Tables, Contracts Table, & Preferred Alternative. (2) The Financial tables show full lifecycle of the program. | Security sections have a minimum score of 4. |
| 16-30 | Marginal: Much work remains to solidify the Exhibit 300. |  |  |
| 1-15 | Poor: Significant gaps exist in the required categories of the Exhibit 300. |  |  |

Section 5:  Status Coordination

Below is a schedule of the Evaluation activities, as well as responsible parties associated with each activity. OCIO is responsible for coordinating the ratings of the team of SMEs participating in the reviews. OCIO will distribute status updates to the Staff and Services Offices on a bi-weekly basis.

Section 6:  Format of this Guide

The format of each section of this Guide includes:

Exhibit 300 Category/Evaluation Element

- Summary

  - Introduction of the evaluation element.

- Applicable Questions

  - Exhibit 300 sections & related questions (mapped to OMB Circular A-11) to evaluate.

- Criteria

  - Evaluation criteria directly correspond with the OMB scoring categories from BY08. The 1 to 5 rating scale per category is used by OMB, and the scale is set by GSA based on past experience with OMB, as well as other agency best practices. OMB does not publish its rating scale.

  - In each section of this guide, initiatives should target the rating of “4” as the standard for a “good” rating in each evaluation category.

Section 7: President’s Management Agenda

Demonstrating alignment with and contribution to the President’s Management Agenda will result in a strong evaluation within this category.  All managing partner initiatives for an eGovernment or line of business initiative, plus any shared service provider as part of one of those efforts, should complete, and will be evaluated on, section IV of the Exhibit 300.  Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section A: Overview | Q8: Provide a brief summary and justification. Q13: Does this support one of the PMA initiatives? Q13a. Briefly and specifically describe for each selected initiative how this asset directly supports the identified PMA initiatives? Q14: Does this initiative support a program assessed using the Program Assessment Rating Tool (PART)? |
| Part I: Summary And Justification | Section D: Performance Information | Performance Information Table |
| Part IV: Planning for Multi-Agency Collaboration | All | Applicable to eGov/LoB initiatives only. |

The scoring criteria are noted below:

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Only eGov/LoB/ shared service providers can receive a 5 in this category. | 1. All questions are answered. 2. The Project summary indicates the gap filled by this initiative alignment with the PMA, and/or evidence that this is a collaborative initiative that includes industry, multiple agencies, state, and/or local governments. 3. The initiative supports one or more of the PMA initiatives and the description of the contribution is specific and measurable. 4. The initiative identifies outcomes consistent with the PART outcomes, if applicable. 5. The initiative demonstrates that an eGov strategy review is underway (applicable to SS initiatives only). 6. The Performance Goals are consistent with the contribution to the PMA initiatives selected. | 1. At least one of the criteria determining a score of 4 has not been met. 2. The initiative supports one or more of the PMA initiatives, but sound evidence of the contribution/ alignment to the PMA is not clearly defined. | 1. Some of the criteria used to determine score of 4 have not been met. 2. The initiative supports one or more of the PMA initiatives, but little evidence of contribution/ alignment to the PMA exists. | 1. No evidence of contribution/ alignment to the PMA exists. |

Section 8: Project Management

Reflecting the extent to which robust and standard program/project management techniques have been employed in managing the effort, a successful evaluation in the Project Management category relies not only on sound responses to project management specific questions, but also on the overall quality of the Exhibit 300. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section A: Overview | Q10: Did the PM review the Exhibit 300? Q11: Contact information of Project Manager? Q11a: What is the current FAC-P/PM certification level of the project/program manager? Q16: What is the level of the IT Project? Q17. What project management qualifications does the PM have? |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, successful completion and very strong responses in other areas of the Exhibit 300, including Risk, Acquisition, Alternatives Analysis, Cost and Schedule, and Performance Tables. | 1. All questions are answered. 2. The response to Question 10 is "Yes." 3. The level of the initiative is compliant with the Federal CIO Council Guidance. 4. The PM is validated as qualified for this initiative: FAC –P/PM. 5. Successful completion and sound responses in other areas of the Exhibit 300, including Risk, Acquisition, Alternatives Analysis, Cost and Schedule, and Performance Tables. | 1. All questions are answered. 2. The response to Question 10 is "Yes." 3. The level of the initiative is compliant with the Federal CIO Council Guidance. 4. The PM meets or is in training to meet minimum FAC-P/PM certification requirements for this initiative. 5. Minor weaknesses exist in other sections of the Exhibit 300. | 1. All questions are answered. 2. The response to Question 10 is "Yes." 3. The level of the initiative is compliant with the Federal CIO Council Guidance. 4. The PM does not meet the FAC-P/PM qualifications. 5. Minor weaknesses exist in other sections of the Exhibit 300. | 1. A PM has not yet been assigned to this initiative. 2. Not all questions are answered. |
| Note: The evaluation for the PM category will be dependent on the ratings for the remaining 9 OMB categories. The PM rating can only be evaluated as high as the lowest rating of the remaining 9 categories. |

Section 9: Acquisition/Contract Strategy

Demonstrating a sound acquisition strategy and plan for current and future contracts will result in a strong evaluation within this category. Integrating other management practices, such as EVM, Section 508 compliance, and performance based contracting, within acquisition plans contribute to successful evaluation. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section A: Overview | Q11a: What is the current FAC-P/PM certification level of the project/program manager? |
| Part I: Summary And Justification | Section C: Acquisition/Contract Strategy | All |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative is aligned with other relevant Exhibit 300 sections, including the Summary of Spending and Performance Baseline Tables. | 1. All questions are answered and the Contracts Table is complete. 2. Answered Yes to the following: (a) competitively awarded; (b) performance-based; (c) EVM in contract or provided valid explanation on why not; (d) contains security and privacy clauses; (e) ensures 508 compliance - or provided valid N/A response; and (f) approved acquisition plan in place. 3. The CO has been certified to the appropriate level. 4. Acquisition Plan date provided. 5. FAC-P/PM certification level is certified to the appropriate level. | 1. At least one of the criteria determining a score of 4 has not been met. | 1. Some of the criteria used to determine a score of 4 have not been met. | 1. Most of the criteria used to determine a score of 4 have not been met. |

Section 10: Performance Goals

Creating outcome-based or business focused performance goals that demonstrate quantifiable improvements are at the core of successful performance goals and their evaluation. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section D: Performance Goals | All |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative is fully consistent with other performance sources, including the PART. | 1. All questions are answered and the Performance Table is complete. 2. Performance measures are outcome-based and are stated as measures (e.g., Number of…, % of…, etc.) Direction, e.g. increasing, decreasing, should be clearly identified. 3. Four PRM outcome- oriented performance goals are listed for each measurement area for at least three years (07, 08, and 09). 4. Measurement Indicator, Baseline, Target, and Actual Results show quantifiable data with an incremental improvement over time. 5. Actual Results are provided for 06 and at least partial results for 07. | 1. At least one of the criteria determining a score of 4 has not been met. | 1. Some of the criteria used to determine a score of 4 have not been met. | 1. Most of the criteria used to determine a score of 4 have not been met. |

Section 11: Security

Being consistent, accurate, and compliant are key to being successful in the Security category. Security data and indicators should be consistent with Federal Security Management Act (FISMA) and supporting security documentation. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section E: Security & Privacy | Questions/Tables 1-7 |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative has no security remediation requirements identified through PART Assessments, OMB high risk reports, or GAO/IG audits. | 1. All questions are answered and the applicable Security Tables (Q3 & Q4) are complete. No weaknesses exist in Section E responses. 2. If the initiative shows DME funding in the Summary of Spending Table, the Systems in Planning Security Table (Q3) is complete. All dates in this table are posted as future dates. The planned C&A date in this table occurs prior to the planned operational date. 3. If the initiative shows O&M funding in the Summary of Spending Table, the Operational Systems Security Table (Q4) is complete. 4. C&A completed within 3 years prior to OMB BY submission for all operational systems (Q4). 5. Control testing completed within one year prior to OMB BY submission for all operational systems. 6. Security Contracting Procedures (Q7) are described in detail, and specific to the initiative. 7. Q1 & Q2 have "Yes" responses. | 1. At least one of the criteria determining a score of 4 has not been met. | 1. Some of the criteria used to a determine score of 4 have not been met. | 1. Most of the criteria used to determine a score of 4 have not been met. |

Section 12: Privacy

Being consistent, accurate, and compliant are key to a successful evaluation in the Privacy category. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section E: Security & Privacy | Questions/Tables 1-7 |
| Part I: Summary And Justification | Section A: Overview | Question 22: Contact information of individual responsible for privacy questions. |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative has no privacy remediation requirements identified through PART Assessments, GAO/IG audits, etc. | 1. All columns of the Privacy Table 8 have been completed for all systems identified in the Security tables. 2. Privacy contact information is provided. 3. No weaknesses exist in response to Privacy questions. | 1. At least one of the criteria determining a score of 4 has not been met. | 1. Some of the criteria used to determine a score of 4 have not been met. | 1. Most of the criteria used to determine a score of 4 have not been met. |

Section 13: Enterprise Architecture

Demonstrating sound alignment with the One GSA EA will result in strong evaluation results within this category. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I: Summary And Justification | Section F: Enterprise Architecture | All |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| 1. Initiative has a “business segment aligned” current and target architecture. 2. Initiative is included in the One GSA EA Transition Strategy & Sequence Plan. 3. Initiative demonstrates alignment to OMB FEA Reference Models. 4. Initiative has demonstrated alignment to and reuse of Government-wide initiatives such as those contained in published Federal Transition Framework. | 1. Initiative has a “business segment aligned” current and target architectures and are included in One GSA EA Target Architecture. 2. Initiative is included in the One GSA EA Transition Strategy & Sequence Plan. 3. OMB required FEA mapping (SRM & TRM) have no deficiencies in any table. 4. Initiative has not demonstrated alignment to and reuse of relevant Government-wide initiatives such as those contained in published Federal Transition Framework. | 1. Initiative has a “business segment aligned” current and target architecture included in One GSA EA. 2. Initiative is not included in One GSA EA Transition Strategy and Sequencing plan. 3. OMB required FEA mapping (SRM & TRM) have a few deficiencies in one or more tables. | 1. Initiative has a “business segment aligned” current and target architecture but is not included in One GSA EA. 2. Initiative is not included in One GSA EA Transition Strategy and Sequencing plan. 3. OMB required FEA mapping (SRM & TRM) have substantive deficiencies in one or more tables. | 1. Initiative does not have a “business segment aligned” current or target architecture. 2. No resources identified to produce architecture artifacts. 3. OMB required FEA mapping (SRM & TRM) have substantive deficiencies in one or more tables. |

Section 14: Cost & Schedule Performance

Demonstrating evidence of compliance with the EVMS ANSI standard for DME funds, and for successfully completing an operational analysis for O&M funds provides a basis for successful evaluation in Cost and Schedule Performance. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part II (Planning, Acquisition, & Performance Information), III (Operations & Maintenance), IV (Multi-Agency Collaboration) | II, IV- Section C - Cost & Schedule Performance III - Section B Cost & Schedule Performance | All |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative has strongly demonstrated the use of an EVMS that meets ANSI/EIA Standard 748 for both government and contractor costs. | 1. Initiative meets EVMS ANSI/EIA Standard 748. For O&M initiatives, an operational analysis completed and current within one year of OMB BY submission. 2. Cost & Schedule variances are within 10%. 3. Milestones are robust, descriptive, and follow the structure outlined by the GSA E300 Guidance. DME milestones no longer than 3-6 months; SS milestones no longer than 1 year. 4. Milestone costs consistent with other sections of the Exhibit 300, including SoS, Contracts Table, & Alternatives Analysis. | 1. At least one of the criteria determining a score of 4 has not been met. | 1. Some of the criteria used to determine score of 4 have not been met. | 1. Most of the criteria used to determine score of 4 have not been met. |

Section 15: Alternatives Analysis

Documenting quantitative and qualitative benefits and costs for the status quo plus three reasonable alternatives is a minimum foundation for a successful evaluation in the Alternatives Analysis section.  Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part II (Planning, Acquisition, & Performance Information) & IV (Multi-Agency Collaboration) | Section A: Alternatives Analysis | All |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| All criteria are met allowing for a score of 4. Additionally, the initiative's chosen alternative aligns from a cost perspective with the SoS, Performance Baseline, and other tables. | 1. Risk-adjusted life cycle costs and benefits have been calculated. 2. The AoA date is within 3 years prior to OMB BY submission. 3. The AoA includes the Status Quo + 3 alternatives. 4. Q3 includes a sound explanation with quantitative benefits (e.g., NPV, ROI, etc.). 5. Q4 includes a sound explanation with qualitative benefits. | 1. At least one of the criteria determining a score of 4 has not been met. 2. The AoA includes the Status Quo + 3 alternatives. | 1. Some of the criteria used to determine score of 4 have not been met. | 1. Most of the criteria used to determine score of 4 have not been met. |

Section 16: Risk Management

Demonstrating a formal approach to risk management along with integrating risk into financial aspects are key to a successful evaluation in Risk Management. Applicable questions include:

| Section | Section | Question |
| --- | --- | --- |
| Part I | Section E: Security | Q2: Is identifying and assessing security and privacy risks a part of the overall risk management effort for each system supporting of part of this investment? Table 3/Table 4 - Security Tables |
| Part II (Planning, Acquisition, & Performance Information), III (Operations & Maintenance), IV (Multi-Agency Collaboration) | II, IV- Section B - Risk Management III - Section A - Risk Management | All |
| Part II (Planning, Acquisition, & Performance Information) & IV (Multi-Agency Collaboration) | Section A: Alternatives Analysis | Q2: Risk Adjusted Benefit/Cost Estimate |

The scoring criteria are noted below.

| 5 Points | 4 Points | 3 Points | 2 Points | 1 Point |
| --- | --- | --- | --- | --- |
| 1. All criteria are met allowing for a score of 4. 2. Additionally, the evidence of sound risk management practices exist within the relevant sections of the Exhibit 300, including Performance Goals and Alternatives Analysis. | 1. Risk-adjusted life cycle costs and benefits have been calculated. 2. The initiative has a risk management plan. 3. The date of the risk management plan is current prior to 3 years of OMB BY submission). 4. Sound description of how investment risks are reflected in life cycle cost estimate and investment schedule. 5. Valid responses within the Security section, including a C&A within 3 years. 6. A valid and current Risk Management Plan has been sent to OCIO. | 1. At least one of the criteria determining a score of 4 has not been met. 2. A Risk Management Plan does exist and is current within 3 years prior to OMB BY submission. | 1. Some of the criteria used to determine score of 4 have not been met. 2. The risk management plan is not current. | 1. Most of the criteria used to determine score of 4 have not been met. 2. No risk management plan exists. |

# Footnotes

OMB Circular A-11, Part 300, Planning, budgeting, acquisition, and management of capital assets. May 2007. Available at http://www.whitehouse.gov/omb/circulars/a11/02toc.html.

Per OMB Memorandum 05-23 that establishes the OMB Management Watch List (I only see references for High Risk List).  Perhaps strike.

Project Management Institute, Project Management Body of Knowledge ®; OMB Capital Programming Guide (June 2006).

GSA EMVS Guide to Implementing the ANSI Standard. Available at http://insite.gsa.gov/Insite/gsa/ep/contentView.do?programId=8793&channelId=-9205&ooid=10480&contentId=10483&pageTypeId=8624&contentType=GSA_BASIC&programPage=%2Fep%2Fprogram%2FgsaBasic.jsp&P=IPC