# Program Plan

# For The

Geospatial Enterprise Architecture Community of Practice Working Group

A Companion Document to the GEA COP Working Group Charter

22 June 2005

# 1.	Introduction:

This program plan has been developed to assist in facilitating and advancing the goals of the Geospatial Enterprise Architecture Community of Practice (GEA COP) Working Group to cooperatively develop and implement an Enterprise Architecture Geospatial Profile.   Although the intent of this profile is to become a baseline document of the Federal Enterprise Architecture, the GEA COP Working Group envisions the Geospatial Profile as a national asset for use by federal, state, local and tribal organizations, as well as businesses in advancing geospatially enabled enterprise architectures.

This document is created in accordance with the GEA COP WG Charter ratified by the Federal CIO Council and the US FGDC.

# 2.	Major Tasks:

Work performed under this program plan will be accomplished by members of the GEA COP WG, with facilitation, project management and architecture support provided by the Open Geospatial Consortium, Inc (OGC) under contract to the US FGDC.  Specific program plan tasks include:

## Task 1 - Education, Outreach, and Geospatial Enterprise Architecture Scoping / Concept Formation

GEA COP WG members will conduct biweekly work sessions, with planning and facilitation support provided by FGDC consultants, to provide training on Enterprise Architecture (EA) concepts, identify progress by government organizations in advancing geospatially enabled Enterprise Architectures, and to identify and organize important artifacts related to work performed to date by participants.  This Task will also focus on the development of key use case scenarios that will address critical provider and user processes and the data behind them involving key stakeholder organizations.  This education and discovery task will be completed by July 2005, and will utilize an open process to involve a diversity of qualified OGC member organizations in meeting task objectives.  Task 1 deliverables include:

    - Refined Project Plan to include refined scope, objectives, and schedule

    - Planning and conduct of educational and informational meetings to familiarize selected US Government and other representatives on Enterprise Architecture concepts, the FEA, EA modeling tools and use case generation (see meeting schedule in section 4 below).

    - Develop two or more use cases to describe inter-agency activities with respect to the EA for NSDI.

    - Use Cases expressed in EA modeling language

    - Meeting notes captured from all meetings

## Task 2 - Development of EA Reference Model Documentation

This project task will focus on consensus development of the Geospatial Enterprise Architecture Profile document consistent with the FEA.  As part of developing this profile, the GEA COP WG will identify and coordinate relevant recommended updates to existing FEA Performance Reference Model (PRM), Business Reference Model (BRM), Service Component Reference Model (SRM), Data and Information Reference Model (DRM), and Technical Reference Model (TRM) documentation.

GEA COP WG participants will be able to leverage the Open Geospatial Consortium’s Enterprise Architecture Special Interest Group (EASIG), to enable open and broad access to OGC industry, government and academic member organizations to obtain input and assessment of the developing Geospatial Profile and associated reference architecture / model documentation.  Documentation developed in this task will draw from discussions with designated participants, EA documentation provided by participants for their organizations, and interaction and documentation provided by designated non governmental representatives.

Deliverables for Task 2 will include:

- Draft Geospatial EA Profile – This document will be developed to provide guidance and best practices for consideration by EA developers.  The document will be developed based on collaborative interaction with Geospatial Enterprise Architecture Working Group participants. In development of the Geospatial Profile, GEA COP WG participants will include consideration of other Profiles developed to date for the FEA (Security Profile, Records Management Profile).

- EA SIG Recommendations / Perspectives – documented consensus input from industry based on results of the discussion of this topic as part of OGC’s Enterprise Architecture Special Interest Group.

- Recommended updates / changes to FEA Performance, Business, Service Component, Data and Information, and Technical Reference Models – Documentation representing the representation of the PRM, BRM, SRM, DRM, and TRM as required.

- Updated Geospatial EA Profile Documentation – updated to reflect lessons learned over the duration of task 2. This documentation will be used as the input for Task 3 pilots and for broader coordination with government and industry.

## Task 3 – Development and Execution of Demonstrations and Pilots to Refine and Validate the Geospatial Profile

To the extent resources are available upon completion of tasks 1 and 2, OGC will facilitate the validation and refinement of the Geospatial Profile through active piloting and demonstration of profile guidance and best practices as part of initiatives managed as part of OGC’s Interoperability Program.  OGC processes will be focused on validation of the Profile document via OGC member driven Interoperability Experiments that focus validation and demonstration of access to and application of use cases defined in earlier in this project plan. Geospatial Profile and related Reference Model documents will be updated based on the experiences gained from the experiments.  Specific Task 3 deliverables include:

- One to two GEA COP Interoperability Experiments designed to validate and demonstrate ability of Geospatial Profile guidance to support access and application of multiple data and services for selected USG organizations (Deliverable 3.1)

- Refined Geospatial Profile documentation, along with relevant updates to Reference Models based on experience gained from the Experiments.

- Support for transition of the Geospatial Profile documentation to FEA approval and maintenance by the CIO Council and the FGDC as part of FEA and NSDI initiatives.

# 3.	Other Considerations:

Key to the success of this effort will be the dedication and commitment of GEA COP WG participants to collaboratively develop, review, advance and validate documentation produced under this project plan.  While consultant support has been secured for this effort, resources are insufficient to accomplish objectives without significant GEA COP participant involvement in meetings, document authoring and pilot initiative development and conduct.

Those FGDC and other GEA COP WG participating organizations that hold membership in the OGC will be required to introduce, formalize and manage pilot initiatives as part of OGC’s Interoperability Program.  OGC consultant staff will assist the GEA COP participants where possible to position these initiatives for introduction into the OGC process.

The ability to express Reference Models in EA modeling language is dependent on the availability of appropriate government furnished software tools for use by GEA COP participants and program consultants.

# 4.	Schedule of Deliverables:

The GEA WG has identified that all tasks and deliverables be completed by 30 September 2005.  The following schedule applies to the tasks detailed above:

| Task Title | Task Reference | Date Due |
| --- | --- | --- |
| Refined Project Plan | 1.a | 30 Jun 2005 |
| Educational / Informational Meetings | 1.b | 30 Jul 2005 |
| Use Case Development | 1.c | 30 Jun 2005 |
| Use Cases in EA Modeling Language | 1.d | 30 Jul 2005 |
| Meeting Notes | 1.e | 30 Sep 2005 |
| Draft Geospatial Profile Document | 2.a | 31 Jul 2005 |
| Industry Input Via OGC EA SIG | 2.b | 31 Aug 2005 |
| Recommended updates to FEA Reference Models | 2.c | 31 Jul 2005 |
| Updated Geospatial Profile Document for Coord. | 2.d | 31 Aug 2005 |
| GEA COP Interoperability Experiment and Report | 3.a | 30 Sep 2005 |
| Final Geospatial Profile and Reference Model Doc | 3.b | 30 Sep 2005 |
| Transition of results to the FGDC & CIO Council | 3.c | 30 Sep 2005 |

# 5.	Meeting Schedule

The success of this effort is largely based on the ability of the GEA COP WG participants to share experiences, collaborate on common goals and actions, and coordinate their work activities.  A series of GEA COP WG meetings has been scheduled to facilitate this interaction.  Additional meetings will be convened as required to address the interests of the WG.   Details on the location, start time and duration of these meetings will be announced in advance by email to the WG list:

| Date | Format |
| --- | --- |
| 1 June 2005 | Face to Face |
| 22 June 2005 | Teleconference |
| 29 June 2005 | Face to Face |
| 6 July 2005 | Teleconference |
| 20 July 2005 | Face to Face |
| 3 August 2005 | Teleconference |
| Biweekly thereafter | To be scheduled |